## Posting Label
Posting Label
manifestAPI | workstream.initiatives.a6i.io/v1a
workstreamUID | W0
workstreamTitle | Cloud value proposition
program | Amplify
initiative | S1
scenario | Default
data.kind.1 | workstream-milestone
data.range.1 | B2:I100
data.sheet.1 | Milestones
data.kind.2 | workstream-metric
data.range.2 | B2:L100
data.sheet.2 | Metrics
organization | My Corp
knowledgeBase | Production
scoringCycle | Dec 2020
scoringMaturity | Draft
estimatedBy | joe.theworkstreamlead@mycorp.com
estimatedOn | 2021-04-29
recordedBy | jill.theinitiativepmo@mycorp.com

## Milestones
Milestones
UID | Theme | Milestone | Date due | Task | Task Date | Dependency | Dependent on
| Assess market opportunity | Assess high monetizability potential segments for Finastra | 2021-06-30 | Analyze current cloud revenue | 2021-06-30
|  |  |  | Assess FS adoption of competitor cloud solutions | 2021-06-30
|  |  |  | Assess FS demand for cloud (via the field) and identify high-value segments (assuming current product-based product strategy) | 2021-06-30 | Engagement with field | Field organization
|  |  |  | Analyze gaps in Finastra's ability to serve demand | 2021-06-30
|  |  |  | Measure lost opportunity because of product gaps | 2021-06-30
| Identify a better product strategy | Market research to re-calibrate product strategy | 2021-10-15 | Jobs-to-be-done / persona research and analysis for the previously identified high-value segments | 2021-08-31 | Resourcing and access to customers | Eli for resourcing TBD for customer access
|  |  |  | Recommendation of Value Propositions | 2021-08-31
|  |  |  | Prototype UX for recommended value propositions | 2021-10-15
|  |  |  | Validation of prototypes with customers | 2021-10-15
|  | Estimate funding gaps and model acceleration curves (MTP) | 2021-11-30 | Redo market sizing against the identified value props (for the high-value segments) |  | Finance and Product owners engagement needed
|  |  |  | Determine adjustments to roadmaps implied by value props |  | Product owners engagement needed
|  |  |  | Quantify any funding gaps required to adjust roadmaps and articulate an ROI business case |  | Finance and product owners engagement needed
|  | Decision to alter roadmaps | 2021-12-15 | Eli Rosner go/no-go on funding and strategy change |  | Funding and approval | Eli Rosner
Presentation to ELT
| Regular updates | Refresh product strategy for FY 23 | 2022-08-31
|  | Refresh product strategy for FY 24 | 2023-08-31

## Metrics
Metrics
UID | Metric | Metric Type | Granularity | Definition of metric | Baseline Value | FY 22 Target | FY 23 Target | FY 24 Target | Source | Frequency of Collection
| Cloud product strategy | R | ELT | Degree of completion product strategy for the year to accelerate cloud revenue | 0% | 100% | 100% | 100% |  | Quarterly
| Fidelity to plan | P | ELT | Deliver agreed milestones on agreed dates | NA | 100% | 100% | 100% |  | Quarterly