## Posting Label
Posting Label
manifestAPI | workstream.initiatives.a6i.io/v1a
workstreamUID | W3
workstreamTitle | N-1 (FusionCloud) and N-3 (FMS, Partner hosted) compliance Cloud value proposition
program | Amplify
initiative | S1
scenario | Default
data.kind.1 | workstream-milestone
data.range.1 | B2:I100
data.sheet.1 | Milestones
data.kind.2 | workstream-metric
data.range.2 | B2:L100
data.sheet.2 | Metrics
organization | My Corp
knowledgeBase | Production
scoringCycle | Dec 2020
scoringMaturity | Draft
estimatedBy | joe.theworkstreamlead@mycorp.com
estimatedOn | 2021-04-29
recordedBy | jill.theinitiativepmo@mycorp.com

## Milestones
Milestones
UID | Theme | Milestone | Date due | Task | Task Date | Dependency | Dependent on | Notes
| Sales process gates | Integrate N-1 / N-3 IT gates in all cloud sales cycles | 2021-09-30 | Mandatory N-1/N-3 and cloud type tags and IT approval gate added to Salesforce | 2021-07-31
|  |  |  | Roll out a tracker artifact and a process to log each upgrade /go live per customer noting what product release was applied. | 2022-08-31 | Product owners (CPTO) and release managers (IT) jointly need to set this up and regularly post information | W1, W7
|  |  |  | Sales teams instructed in populating indicators. | 2021-08-31 |  | W4, W5
|  |  |  | Sales teams populate all outstanding opportunities. | 2021-09-30 | Sales teams | W4, W5 | Conferred with Barbara Kochman on 6/5/21 - will be much easier and faster if we only populate opportunities on a go-forward basis.
| N-1/N-3 compliance reporting | Set up monthly N-1/N-3 reporting | 2021-11-30 | Monthly N-1/N-3 release reports generated. | 2021-10-31
|  |  |  | Monthly N-1/N-3 ongoing compliance reports generated. | 2021-11-30
| Compliance with N-1 / N-3 | Deliver >25% N-1/N-3 compliance | 2022-05-31 |  |  | Depends on product to support CI/CD (W1). Depends on operator to vigorously upgrade (W2, W7) | W1, W2, W7
|  | Deliver >50% N-1/N-3 compliance | 2023-05-31 |  |  | Depends on product to support CI/CD (W1). Depends on operator to vigorously upgrade (W2, W7) | W1, W2, W7
|  | Deliver >75% N-1/N-3 compliance. | 2024-05-31 |  |  | Depends on product to support CI/CD (W1). Depends on operator to vigorously upgrade (W2, W7) | W1, W2, W7

## Metrics
Metrics
UID | Metric | Metric Type | Granularity | Definition of metric | Baseline Value | FY 22 Target | FY 23 Target | FY 24 Target | Source | Frequency of Collection
| GA variance | R | ELT | Across all customer environments, compute the N-x, average the "x" values, and report that. | TBD | TBD | TBD | 1 | W3 centralized workbook | Quarterly
| Go-live N-x compliance | P | ELT | Count of cloud deals signed. Calculate ratio of implementations meeting N-1 (FusionCloud, Partner Managed Services) or N-3 (FMS) compliance. The compliance is measured as of go-live time (i.e., once implementation completes). Count begins as of implementation of IT approval gate to capture deal close. | TBD | TBD | TBD | 1 | W3 centralized workbook | Quarterly
| GA variance - FusionCloud | R | Per growth product | Across all customer environments, compute the N-x, average the "x" values, and report that. | TBD | TBD | TBD | 1 | W3 centralized workbook | Quarterly
| GA variance - FMS | R | Per growth product | Across all customer environments, compute the N-x, average the "x" values, and report that. | TBD | TBD | TBD | 3 | W3 centralized workbook | Quarterly
| GA variance - MSP | R | Per growth product | Across all customer environments, compute the N-x, average the "x" values, and report that. | TBD | TBD | TBD | 1 | W3 centralized workbook | Quarterly
| Compliance at go-live for FusionCloud | P | Per growth product | Count of FC deals signed. Calculate ratio of implementations meeting N-1 compliance, per type vs. deal close. Count begins as of implementation of IT approval gate to capture deal close. | TBD | TBD | TBD | 1 | W3 centralized workbook | Quarterly
| Compliance at go-live for FMS | P | Per growth product | Count of FMS deals signed. Calculate ratio of implementations meeting N-3 compliance, per type vs. deal close. Count begins as of implementation of IT approval gate to capture deal close. | TBD | TBD | TBD | 3 | W3 centralized workbook | Quarterly
| Compliance at go-live for Partner Managed Services Managed Service Providers | P | Per growth product | Count of MSP deals signed. Calculate ratio of implementations meeting N-1 compliance, per type vs. deal close. Count begins as of implementation of IT approval gate to capture deal close. | TBD | TBD | TBD | 1 | W3 centralized workbook | Quarterly
P = Progress metric
R = Results metric

## Project Plan
Project status | Green
Project AMPlify S.1 W3 - N-1 Project Plan | Description | Start | Planned End | Actual End | Resources | Status/details | Links
Initiate
Project AMPlify charter created | Meet with project charter leads and discuss program | 2021-05-06 | 2021-05-06 | 2021-05-06 | Alejandro Hernandez; | initial discussions as to who should own this task | https://finastra.sharepoint.com/teams/ProjectAMPlify-CentralTeam/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=GkcfcN&cid=33eaca74%2D7ec9%2D4cb2%2Db2f3%2D3237192fbcab&FolderCTID=0x012000B484E4D71F828A4890A5DC8F8758B410&viewid=438f7de9%2D5fca%2D42ed%2Da51e%2D1702da22a5e8&id=%2Fteams%2FProjectAMPlify%2DCentralTeam%2FShared%20Documents%2FGeneral%2FAMPlify%20Strategic%20Initiatives%2FS1%2E%20Accelerate%20cloud%2F03%20Workplan%2FMilestones%2Fs1%2Ew3
S.1 W3 - N-1 Workstream assignment | Review N-1 workstream and validate ownership (IT vs. Product) | 2021-05-07 | 2021-05-20 | 2021-05-20 | Alejandro Hernandez; | IT to manage this workstream - details confirmed.
Define
Define workstream goals | Define goals for this workstream for Fusion Cloud and FMS solutions. | 2021-05-20 | 2021-06-01 | 2021-06-01 | Alejandro Hernandez; | Goals set
Define workstream milestones | Define milestones for this project | 2021-05-20 | 2021-06-01 | 2021-06-01 | Alejandro Hernandez; | milestones set
Define workstream Metrics | R, P metrics created | 2021-06-01 | 2021-06-01 | 2021-06-01 | Alejandro Hernandez; | Metrics created.
Define FY 22, FY 23 FY24 goals | Define the goals for this program for N-1 (FC, MSP) and N-3(FMS) solutions, using baseline numbers to estimate resonable goals. | 2021-06-01 | TBD | TBD | Alejandro Hernandez; | Using baseline numbers, define reasonable goals for this project.
Execution
Salesforce updates |  | 2021-06-01 | 2021-07-31
Identify process for adding fields/gates to SF | Meet with Barbara Kochman to discuss process of adding fields and processes to Salesforce. | 2021-06-04 | 2021-06-07 | 2021-06-10 | Barbara Kochman | Salesforce has a 2 week release cycle. Need use cases to validate request for new gate and fields.
Obtain ON for Essence opportunities that did not follow GS Opportunity Workflow process | Need use cases to justify changes to Salesforce (new fields and IT approval gate) | 2021-06-10 | 2021-06-15 | 2021-06-15 | Sreesha Rao | ON 190243 - Essence in Angola - closed 2/26/21 ON196867 - Essence in Germany - closed 5/3/21
Create powerpoint documentation describing the new fields (N-1/N-3) and IT Approval gate process | Documentation should be provided with Servicenow ticket for documenting and validating Salesforce changes | 2021-06-22 | 2021-06-25 |  | Manno
Create Servicenow ticket to request new fields for Salesforce | Servicenow tickets will be the method of creating the changes to Salesforce. We will need to attach use cases to show reason for new IT Approval gate. Utilize Essence opportunities. | 2021-06-25 | 2021-06-30 |  | Barbara Kochman | 6/10/21 - Barbara reviewed process with me. She needs Servicenow ticket to make changes during 2 week cycles. Do NOT make retroactive - will speed up process.
Mandatory N-1/N-3 and cloud type tags and IT approval gate added to Salesforce | Milestone | 2021-06-01 | 2021-07-31 |  | Barbara Kochman
T20 Process enhancements |  | 2021-06-15 | 2021-08-31
Upgrade existing Opportunity tracking sheet for all LOBs | Create a new, centralized, cross-LOB tracking sheet, based upon existing ROW sheet created by Sreesha Rao. | 2021-06-15 | 2021-06-30 |  | Sreesha Rao | 6/14/21 - added 3 new fields to existing tracking sheet created by Sreeshafor TCM and ROW. 6/15/21 - conferred with Sreesha - we need a new, centralized workbook created to expand for all LOBs. | https://finastra.sharepoint.com/teams/TCMCBRBROWEnterpriseManagementReporting/Lists/Retail%20ROW%20Deals/AllItems.aspx
Enhance T2O process to include updating of centralized worksheet for Opportunities N-1 status and go-live date for all LOBs | Incorporate update of centralized client implementation tracking worksheet into the T2O process to allow tracking of metrics for N-1 (FC, MSP) and N-3 (FMS) compliance. | 2021-06-30 | 2021-07-30 |  | Devyansh Kaura | Devyansh will work to get this update process included in the T2O
Roll out a tracker artifact and a process to log each upgrade /go live per customer noting what product release was applied. | Milestone | 2021-06-01 | 2021-08-31
Sales team training |  | 2021-09-01 | 9/31/21
SF Gate and new field training |  |  | 9/31/21 |  | Rudy Kawmi (Eric Duffaut COS) | Rudy heads up training and enablement
Sales Operations training completed for all teams | Milestone |  | 9/31/21 |  | Przemek Oledzki (international);Tom Kimutis (NA);Dan Jacobs
Monitor
Monitor opportunity flow and N-1 compliance
Quarterly reporting
Close