## Posting Label
Posting Label
manifestAPI | workstream.initiatives.a6i.io/v1a
workstreamUID | W6
workstreamTitle | Pricing
program | Amplify
initiative | S1
scenario | Default
data.kind.1 | workstream-milestone
data.range.1 | B2:I100
data.sheet.1 | Milestones
data.kind.2 | workstream-metric
data.range.2 | B2:L100
data.sheet.2 | Metrics
organization | My Corp
knowledgeBase | Production
scoringCycle | Dec 2020
scoringMaturity | Draft
estimatedBy | joe.theworkstreamlead@mycorp.com
estimatedOn | 2021-04-29
recordedBy | jill.theinitiativepmo@mycorp.com

## Milestones
Milestones
UID | Theme | Milestone | Date due | Task | Task Date | Dependency | Dependent on
| Optimize current pricing | Pricing metrics assessment complete | 2021-08-31 | Dev cost data made available | 2021-07-31 | Finance, product team | W1
|  |  |  | Cloud / operating Cost data made available | 2021-07-31 | Finance, cloud operator (W2, W7) | W2, W7
|  |  |  | Correct pricing metrics defined to monetize each product. | 2021-08-31
| Define future pricing model | Target pricing model published | 2021-11-30 | Competitive intelligence data available. |  | Market cloud demand analysis | W0
|  |  |  | Customer value hypothesise feedback quantified & qualified |  | Identification of agreed cloud value propositions | W0
[6 empty] | Feature/function taxonomy that could be independently monetized | W1
Cloud pricing approved by Pricing Committee

## Metrics
Metrics
UID | Metric | Metric Type | Granularity | Definition of metric | Baseline Value | FY 22 Target | FY 23 Target | FY 24 Target | Source | Frequency of Collection
| Pricing readiness | R | ELT | Pricing approach developed and implemented by the time any cloud product launches | TBD | 100% | 100% | 100%
| Pricing definition plan | P | ELT | Pricing plan progress for products that will be launched in the next 6 months | TBD | 100% | 100% | 100%
| Pricing readiness per product | R | Growth products | Pricing approach developed and implemented by the time any cloud product launches | TBD | 100% | 100% | 100%
| Pricing definition plan per product | P | Growth products | Pricing plan progress for products that will be launched in the next 6 months | TBD | 100% | 100% | 100%