## Posting Label
Posting Label
manifestAPI | workstream.initiatives.a6i.io/v1a
workstreamUID | W7
workstreamTitle | IT role in cloud native solutions
program | Amplify
initiative | S1
scenario | Default
data.kind.1 | workstream-milestone
data.range.1 | B2:I100
data.sheet.1 | Milestones
data.kind.2 | workstream-metric
data.range.2 | B2:M30
data.sheet.2 | Metrics
organization | My Corp
knowledgeBase | Production
scoringCycle | Dec 2020
scoringMaturity | Draft
estimatedBy | joe.theworkstreamlead@mycorp.com
estimatedOn | 2021-04-29
recordedBy | jill.theinitiativepmo@mycorp.com

## Milestones
Milestones
UID | Theme | Milestone | Date due | Task | Task Date | Dependency | Dependent on
| Skills fit for future | Talent Development / sourcing plan in place | 2021-11-30 | Skills assessment | 2021-08-31
|  |  |  | Role segmentation | 2021-11-30
|  | Deliver FY 22 skills-for-the future roadmap | 2022-05-31 | Meet target of 5% of new hires | 2022-02-28
|  | Deliver FY 23 skills-for-the future roadmap | 2023-05-31 | Meet target of 15% of new hires | 2023-05-31
|  | Deliver FY 24 skills-for-the future roadmap | 2024-05-31 | Meet target of 30% of new hires | 2024-05-31
| Incident optimisation | Dashboard mapping incidents to revenue at risk | 2022-09-28 | Start mapping | 2021-11-30
|  |  |  | First 3 products mapped and dashboard 50% automated | 2022-02-28
|  |  |  | All priority products mapped and dashboard 90% automated | 2022-05-31
|  | Service status | 2023-02-28 | Prioritize scope | 2022-05-31
|  |  |  | Complete Phase I | 2022-10-31
|  |  |  | Complete Phase II | 2023-06-28
|  | Automation | 2023-02-28 | Prioritize high-impact recurring events as a good fit for automation | 2022-05-31
|  |  |  | Complete Phase I | 2022-10-31
|  |  |  | Complete Phase II | 2023-06-28
|  | Deliver FY 23 incident optimization roadmap | 2023-05-31 | Address 70% of priority products | 2023-05-31
|  | Deliver FY 24 incident optimization roadmap | 2024-05-31 | Address 95% of priority products | 2024-05-31
| Modernized network | Definition of priorities and target state | 2021-09-28 | Agreement on network operating model & prioritization of network | 2021-10-31
|  | Deliver modernization network roadmap for FY 22 | 2022-05-31 | 20% of network priorities delivered | 2021-11-30
|  |  |  | 10% of clients onboarded to modernized network | 2022-05-31
|  | Deliver modernization network roadmap for FY 23 | 2023-05-31
|  | Deliver modernization network roadmap for FY 24 | 2024-05-31
| TCO | TCO system and process implementation roadmap | 2023-06-02 | Prioritise products / solutions for reporting | 2022-01-27 | W0
|  |  |  | Create standardised scorecard | 2022-03-27
|  |  |  | Automate data gathering and visualization | 2023-06-02
|  |  |  | Agree framework for TCO | 2021-12-31
|  | TCO reporting for 1st product | 2022-05-01
|  | TCO reporting 2nd product | 2022-08-01
|  | TCO rollout for additional priority products in FY 23 | 2023-05-31
|  | TCO rollout for additional priority products in FY 24 | 2024-05-31
| E2E Lead to cash | Adjust our corporate applications to adopt and support different methods of revenue and lead to cash | TBD | Identify use cases and lead to cash models with stakeholders |  | W0
|  |  |  | Define & deliver Phase I |  | 42
|  |  |  | Define & deliver Phase II |  | 43

## Metrics
Metrics
UID | Metric | Metric Type | Granularity | Definition of metric | Baseline Value | FY 22 Target | FY 23 Target | FY 24 Target | Source | Frequency of Collection | Weighting
| Skills, Network, Incident, Costs Overall | R | Executive | A combination of weighting and progress to give an overall view of R metrics |  | 15.55% | 33.6% | 56.2% |  | Quarterly
| Skills, Network, Incident, Costs Overall | P | Executive | A combination of weighting and progress to give an overall view of P metrics |  | 40% | 53.5% | 66.5% |  | Quarterly
| Skills agreed & aligned to PP&T | P | IT | Skill based on current and future needs defined and agreed |  | 100% | 100% | 100% |  | Quarterly | 10% | 10% | 10% | 10%
| Staff assessed | P | IT | % of IT staff having assessed to baseline |  | 90% | 90% | 90% |  | Quarterly | 10% | 9% | 9% | 9%
| New hires aligned to segmented need | R |  | Percent of new hires who have the skills needed for the target DevOps operating model |  | 15% | 50% | 80% |  | Quarterly | 15% | 2.25% | 7.5% | 12%
[12 empty] | 0% | 0% | 0%
[12 empty] | 0% | 0% | 0%
| Network federation | P | IT | 95% of prioritized products edge network that is federated |  | 15% | 50% | 100% |  | Quarterly | 10% | 1.5% | 5% | 10%
| Network modernization | P | IT | Degree of completion of modernization roadmap for the network |  | 75% | 95% | 95% |  | Quarterly | 10% | 7.5% | 9.5% | 9.5%
| Clients on modernized network | P | IT | 80% of prioritized products on modernized network |  | 5% | 50% | 100% |  | Quarterly | 10% | 0.5% | 5% | 10%
| Client connections deployment time | R | IT | 50% reduction over current | 120 | 10% | 30% | 100% |  | Quarterly | 10% | 1% | 3% | 10%
| Changes utilizing self-service | R | IT | 75% of deployments utilizing |  | 10% | 50% | 100% |  | Quarterly | 15% | 1.5% | 7.5% | 15%
[12 empty] | 0% | 0% | 0%
[12 empty] | 0% | 0% | 0%
| Service Status Page | P | IT | 100% prioritized products onboarded to status page |  | 0% | 0% | 0% |  | Quarterly | 6% | 0% | 0% | 0%
| Incident Automation | P | IT | Being driven out in next 90 days |  | 0% | 0% | 0% |  | Quarterly | 12% | 0% | 0% | 0%
[12 empty] | 0% | 0% | 0%
[12 empty] | 0% | 0% | 0%
| Mean time to engage | R | IT | 30% reduction in mean time to engage (TBD - working through roadmap) |  | 0% | 0% | 0% |  | Quarterly | 12% | 0% | 0% | 0%
| Mean time to recover | R | IT | 40% reduction of mean time to recover (TBD - working through roadmap) |  | 0% | 0% | 0% |  | Quarterly | 12% | 0% | 0% | 0%
[12 empty] | 0% | 0% | 0%
[12 empty] | 0% | 0% | 0%
| # of products identified and prioritized | P | IT | % of products that have been prioritized and agreed as go forward |  | 100% | 100% | 100% |  | Quarterly | 10% | 10% | 10% | 10%
| Products with TCO completed | P | IT | % of prioritized products completed |  | 15% | 50% | 80% |  | Quarterly | 10% | 1.5% | 5% | 8%
| Reporting 1 | R | IT | TBD |  | 40% | 60% | 80% |  | Quarterly | 12% | 4.8% | 7.2% | 9.6%
| Reporting 2 | R | IT | TBD |  | 50% | 70% | 80% |  | Quarterly | 12% | 6% | 8.4% | 9.6%
[10 empty] | Progress | 88%
[10 empty] | Reporting | 88%