## Posting Label
Posting Label
manifestAPI | workstream.initiatives.a6i.io/v1a
workstreamUID | W2
workstreamTitle | SW Delivery and Production Operations
program | Amplify
initiative | S1
scenario | Default
data.kind.1 | workstream-milestone
data.range.1 | B2:I100
data.sheet.1 | Milestones
data.kind.2 | workstream-metric
data.range.2 | B2:L100
data.sheet.2 | Metrics
organization | My Corp
environment | Production
scoringCycle | Dec 2020
scoringMaturity | Draft
estimatedBy | joe.theworkstreamlead@mycorp.com
estimatedOn | 2021-04-29
recordedBy | jill.theinitiativepmo@mycorp.com

## Milestones
Milestones
UID | Themes | Milestone | Date due | Task | Task Date | Dependency | Dependent on
| FusionOperate Roadmap | Align FusionOperate adoption roadmap to W1 modernization plan | 2021-11-30 | Agree products that adopt FO in FY 22 | 2021-08-15 | Need product list that will adopt FO in FY 22 by July 15 | W1
|  |  |  | Align Quality First Program with FO Test Platform and SRE principles | 2022-11-30 | Steve Moe
|  |  |  | Alignment of FO Edge Networking with IT | 2022-08-31 | Discussions with IT | W7
| FusionOperate Adoption | Delivery of Fusion Operate aggregate adoption targets (gorwth product target and new product target) for FY 22 | 2022-05-31 |  |  | Need product list of products adopting FO in FY 22 | W1
|  | Delivery of Fusion Operate aggregate adoption targets (gorwth product target and new product target) for FY 23 | 2023-05-31 |  |  | Need product list of products adopting FO in FY 23 | W1
|  | Delivery of Fusion Operate aggregate adoption targets (gorwth product target and new product target) for FY 24 | 2024-05-31 |  |  | Need product list of products adopting FO in FY 24 | W1

## Metrics
Metrics
UID | Metric | Metric Type | Granularity | Definition of metric | Baseline Value | FY 22 Target | FY 23 Target | FY 24 Target | Source | Frequency of Collection
M1 | FusionOperate adoption | R | ELT | Aggregation across all products of product-specific metric M3 | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | ea-journeys knowledge base system | Annual
M2 | Test platform, monitoring, pipelines, & dev-owned ops | P | ELT | Aggregation across all products or product-specific metrics M4, M5, M6, M7 | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | TBD 8/31/21 | ea-journeys knowledge base system | Quarterly
M3 | Roadmap delivery | R | Growth products | Metric computed from the 7 FusionOperate adoption indicators that exist for each growth product that is stacked ranked above a threshold (~8 products). Of the 7 indicators, 3 are for W1 and 4 are for W2. Computation procedure is: 1. For a given fiscal year, we sum up the numerical targets across 4 W2 FO indicators * ~8 growth products (~32 numbers added). This is the denominator 2. For the same fiscal year, we measure what the actuals are for these indicators, and add them up (~32 numbers added). This is the numerator 3. Metric is defined as the ratio, defined as a percent. | TBD 8/31/21 | TBD 11/30/21 | TBD 11/30/21 | TBD 11/30/21 |  | Annual
|  | R | New products | Same as above, for for new products instead of growth products. | TBD 8/31/21 | TBD 11/30/21 | TBD 11/30/21 | TBD 11/30/21 |  | Annual
M4 | Quality | P | Growth products | Same as for roadmap delivery, except the sum is only over 1 FO Adoption indicator (the "% FO Test Platform" indicator) | TBD 8/31/21 | TBD 11/30/21 | TBD 11/30/21 | TBD 11/30/21 |  | Quarterly
M5 | Availability | P | Growth products | Same as for roadmap delivery, except the sum is only over 1 FO Adoption indicator (the "% Logs, Metrics & Traces" indicator) | TBD 8/31/21 | TBD 11/30/21 | TBD 11/30/21 | TBD 11/30/21 |  | Quarterly
M6 | Velocity | P | Growth products | Same as for roadmap delivery, except the sum is only over 1 FO Adoption indicator (the "% FO Pipeline" indicator) | TBD 8/31/21 | TBD 11/30/21 | TBD 11/30/21 | TBD 11/30/21 |  | Quarterly
M7 | Operations | P | Per growth product | Same as for roadmap delivery, except the sum is only over 1 FO Adoption indicator (the "% Dev-owned AppOps" indicator) | TBD 8/31/21 | TBD 11/30/21 | TBD 11/30/21 | TBD 11/30/21 |  | Quarterly