## Posting Label
Posting Label
manifestAPI | workstream.initiatives.a6i.io/v1a
workstreamUID | W4
workstreamTitle | FMS / AMS
program | Amplify
initiative | S1
scenario | Default
data.kind.1 | workstream-milestone
data.range.1 | B2:I100
data.sheet.1 | Milestones
data.kind.2 | workstream-metric
data.range.2 | B2:L100
data.sheet.2 | Metrics
organization | My Corp
environment | Production
scoringCycle | Dec 2020
scoringMaturity | Draft
estimatedBy | joe.theworkstreamlead@mycorp.com
estimatedOn | 2021-04-29
recordedBy | jill.theinitiativepmo@mycorp.com

## Milestones
Milestones
UID | Theme | Milestone | Date due | Task | Task Date | Dependency | Dependent on
| Multi cloud strategy | Multi product/ multi cloud certification (4 x 3 certifications: LIQ, GPP, TI, Kondor certified on AWS, Azure, Google) defined as: we can sell and deliver those FMS/AMS for those products on those cloud platforms | Will be determined based on each sales opportunity that requires a new multi-cloud certification. | Per cloud platform and per product, need to get: 1. The product's sizing model to support N users on each cloud platform 2. The additional cost in USD (both one-time and on-going) to modify and /or be able to support the product as incurred by CPTO (i.e., funding that FMS/AMS would need to bake into the deal to fund CPTO costs) 3. Statement to Enterprise Architecture that product has been tested and works on the platform on the stated configuration. 4. Statement from CTPO that it is able and willing to support the product in question on the cloud platform in question, and authorizes FMS/AMS to initiate sales activity. |  | CPTO organization has to schedule this work in response to an opportunity identified by FMS/AMS. Expectation: first time a product is considered, CPTO should complete within 3 months. After that completion/refreshing of analsys should happen within 2 weeks. | W1, W2
| FusionOperation Adoption | Provide feedback and suggested priorities from FMS/AMS to the FusionOperate and modernization roadmaps. | Ongoing | Participate in FusionOperate roadmap feedback session | Quarterly
|  |  |  | Present for potential re-use in product the CBA automated tests scripts that allow CBA to upgrade with no CBA personnel having to test | 2021-08-31
|  | Migration to Fusion Operate | TBD - once FusionOperate is available | Draft migration plan - handle separately "new" vs "old" customers |  | Modernized product | W1, W2

## Metrics
Metrics
UID | Metric | Metric Type | Granularity | Definition of metric | Baseline Value | FY 22 Target | FY 23 Target | FY 24 Target | Source | Frequency of Collection
| FMS revenue | R |  | FMS revenues as per MTP. This is expressed in millions of USD, and excludes FusionCloud and Partner Managed Services (PMS) | 10.91 | 21.0488 | 39.913 | 72.1106 |  | Quarterly
| Margin | R |  | Margins as a % of total operating cost | 22.7% | 33.1% | 35.3% | 36.2% |  | Quarterly
| Clients in pipeline | P |  | Number of clients in FMS workshop funnel | TBD | TBD | TBD | TBD |  | Quarterly
| Bookings | P |  | Bookings | TBD | TBD | TBD | TBD |  | Quarterly