## Posting Label
Posting Label
manifestAPI | workstream.initiatives.a6i.io/v1a
workstreamUID | W5
workstreamTitle | Cloud Sales (excl FMS)
program | Amplify
initiative | S1
scenario | Default
data.kind.1 | workstream-milestone
data.range.1 | B2:I100
data.sheet.1 | Milestones
data.kind.2 | workstream-metric
data.range.2 | B2:L100
data.sheet.2 | Metrics
organization | My Corp
environment | Production
scoringCycle | Dec 2020
scoringMaturity | Draft
estimatedBy | joe.theworkstreamlead@mycorp.com
estimatedOn | 2021-04-29
recordedBy | jill.theinitiativepmo@mycorp.com

## Milestones
Milestones
UID | Theme | Milestone | Date due | Task | Task Date | Dependency | Dependent on
| Optimize execution today | Operational framework | TBC | Agree which product sales classify as cloud for target selling in the strategic initiative
Settting-KPIs framework
|  | Waterfall model to illustrate required timing from idea to first sale | TBC | Document the experiences
|  | Identify synergictic FFDC apps | 2021-06-30 | Identify FFDC apps which drive cloud revenue for Finastra
|  | Prepare sales readiness | 2021-08-01 | Propose means for faster proposal turnarounds (e.g., ready-made connectors to environments to support customer POCs). Refers to: demo infrastructure + FFDC
Identification of cloud champions per region/lob (example: if an Essence opportunity comes along, what experts, field staff capacity, etc. are needed)
| Help product strategy | Ideas for enterprise cloud business | TBC | Document ideas for augmenting/replacing existing/non-existing modules which would better address customer demand for cloud in the enterprise segments
| Go-to-market model | Go-to-market plan template | 2021-08-30 | Template that would be subsequently populated for each cloud value proposition to yield an actionable sales model for such value prop. Template would have swimlanes for:
Routes to market
First target (incl FMS and other building blocks_ to size the price
Demand creation approach
Pricing
Accelerators & incentives
Internal communications on how to hug a tree
People & skills
|  | Create go-to-market model for selected solutions | TBC |  |  | Need modernized product before SaaS sales can start | W1, W2

## Metrics
Metrics
UID | Metric | Metric Type | Granularity | Definition of metric | Baseline Value | FY 22 Target | FY 23 Target | FY 24 Target | Source | Frequency of Collection
| Cloud bookings | R | ELT | Cloud bookings of [$XM] | TBD | TBD | TBD | TBD |  | Quarterly
| FusionCloud revenue | R | ELT | Fusion Cloud revenues as per MTP. This is expressed in millions of USD, and excludes FMS and PMS. | 225.1426 | 234.9261 | 289.7193 | 363.386 |  | Quarterly
| Cloud pipeline | P | ELT | Cloud pipeline by product by region of [$XM] | TBD | TBD | TBD | TBD |  | Quarterly