## Milestones
Milestones
UID | Themes | Milestone | Date due | Task | Task Date | Dependency | Dependent on
| Current Cloud Support Model | Short term E2E Customer Support operating model in place | 2021-08-31 |  |  | Needs / requirements from FMS worksteram | W4
Validate cloud support model for FMS
|  | SFDC & ServiceNow system integration complete | 2021-11-30 | Assess / identify gaps
Implement improvements
| Train support staff | Train 10-15% of Enterprise and FMS support staff for cloud | 2021-11-30 |  |  |  | W4, W5, W9
|  | Train 60% of required support staff across all cloud slutions | 2023-05-31 |  |  |  | W4, W5, W9
|  | Train 100% of required support staff across all cloud slutions | 2024-05-31 |  |  |  | W4, W5, W9
| End state vision / framework for Cloud Support | Digital Cloud Customer Support End State defined | 2021-08-31 | Define requirements for R&D, Cloud Ops and Customer Support
| Finastra support staff becomes more efficient via automation | Achievement of 20% of reduction target for handling root cause analysis tasks through automation | 2022-02-28 |  |  |  | W1
|  | Achievement of 70% of reduction target for handling root cause analysis tasks through automation | 2023-05-31 |  |  |  | W1
|  | Achievement of 100% of reduction target for handling root cause analysis tasks through automation | 2024-05-31 |  |  |  | W1
| Finastra support tasks shifted to customers via automated self service | Achievement of 10% of inflow reduction target through customer self-service | 2022-02-28
|  | Achievement of 60% of inflow reduction target through customer self-service | 2023-05-31 |  |  |  | W1
|  | Achievement of 100% of inflow reduction target through customer self-service | 2024-05-31 |  |  |  | W1
| Drive customer retention via optimizing feature/function benefit | Documentation of the feature/function taxonomy against which we will progresss with customer usage tracking via automation | 2021-11-30 |  |  |  | W1
|  | Achieve 20% feature/function user adoption tracking | 2022-05-31 |  |  |  | W1
|  | Achieve 70% feature/function user adoption tracking | 2023-05-31 |  |  |  | W1
|  | Achieve 100% feature/function user adoption tracking | 2024-05-31 |  |  |  | W1

## Metrics
Metrics
UID | Metric | Metric Type | Granularity | Definition of metric | Baseline Value | FY 22 Target | FY 23 Target | FY 24 Target | Source | Frequency of Collection
| Maturity index for support model | R | ELT | Computed as an average across products of the 3 R metrics below for root cause analysis, self-service and usage tracking |  |  |  | 50% |  | At end of journey
| % of target maturity attained | P | ELT | Ratio of actual maturity index for support to the end-of-journey target maturity index | [5 empty] | Quarterly
| Reduction in person-days to conduct root cause analysis | R | Per growth product | Count number of hours dedicated to RCA, compare to what it was typically at the end of FY 21, and convert to FTE equivalent. |  |  |  | 40% |  | At end of journey
| Reduction in inflow due to self service automation | R | Per growth product | Count number of inflow cases and compare to what it was at the end of FY 21 (normalized for customer growth) |  |  |  | 30% |  | At end of journey
| % of product features/function whose customer usage is trackable via automation | R | Per growth product | Based on a product-provided taxonomy of its monetizable features/functions (possibly hierarchical), we count how many of those have their customer usage tracked via automation |  |  |  | 80% |  | At end of journey
| Plan completeness for reduction in person-days to conduct root cause analysis | P | Per growth product | Count number of hours dedicated to RCA, compare to what it was typically at the end of FY 21, and convert to FTE equivalent, and see what percentage of R metric target has been met |  | 10% | 70% | 100% |  | Quarterly
| Plan completeness for reduction in inflow due to self service automation | P | Per growth product | Count number of inflow cases and compare to what it was at the end of FY 21 (normalized for customer growth), and see what percentage of R metric target has been met |  | 10% | 60% | 100% |  | Quarterly
| Plan completeness for % of product features/function whose customer usage is trackable via automation | P | Per growth product | Based on a product-provided taxonomy of its monetizable features/functions (possibly hierarchical), we count how many of those have their customer usage tracked via automation, and see what percentage of R metric target has been met |  | 20% | 70% | 100% |  | Quarterly