## Posting Label
Posting Label
workstreamUID | W9
workstreamTitle | Talent transformation
program | Amplify
initiative | S1
scenario
environment | Production
scoringCycle | FY 22
scoringMaturity | Draft
estimatedBy
estimatedOn | 2021-05-25
recordedBy | alejandro.hernandez@finastra.com

## Milestones
Milestones
UID | Themes | Milestone | Date due | Task | Task Date | Dependency | Dependent on
| Skills and capabilities | Skills & capabilities gaps assessment | 2021-09-30 | Customer cloud journey mapping to inform assessment
Diagnostic of pre-sales, sales cloud skills
Diagnostic of developers, product managers on cloud skills
Diagnostic of cloud ops, support in cloud skills
Based on target journey and how it maps to current skills in pre-sales and sales, identify the skill gaps in the field organization
|  | Define the intervention plan required to upskill the pertinent teams | 2021-09-30
|  | Deliver FY 22 skills intervention plan | 2021-05-31
|  | Deliver FY 23 skills intervention plan | 2022-05-31
|  | Deliver FY 24 skills intervention plan | 2024-05-31
| Governance & accountability challenges | Mapping of accountabilities for cloud customer journey

## Metrics
Metrics
UID | Metric | Metric Type | Granularity | Definition of metric | Baseline Value | FY 22 Target | FY 23 Target | FY 24 Target | Source | Frequency of Collection
| Skills & capabilities plan | R | ELT | Actions from plans in place (training, hires, capabilities addressed) | 0% | 100% | NA | NA
| Gap analysis roadmap | P | ELT | Completion of roadmap tasks on time | 0% | 100% | NA | NA