## Posting Label
Posting Label
product | Essence
journey | Modernization
planType | Marathon
variant | simple; burnout
scenario | MTP
environment | Production
scoringMaturity | Draft
estimatedBy | Jay, Dipak , Preeta and Saurabh
scoringCycle | FY 22
estimatedOn | 2021-05-25
recordedBy | dipak.ray@finastra.com

## Sheet1
Milestones
[5 empty] | M1 | M2 | M3 (Amplify ends) | M4
|  |  |  | Theme | Improve Essence Cloud cost-to-operate by 10% | Cloud version of ESS ready for EQ migration to ESS cloud | Cloud version of ESS ready for MidAs migration to ESS cloud. Expansion of CAM to Level 3 Bank and increase of revenues to 120 M | 100% of microservices done and Multi-tenant
|  |  |  | Date | Q3 FY22 | Q2 FY 23 | Q4 FY 24 | Q4 FY 25
UID | Big Rock | UID | Breakdown |  | M1 | M2 | Amplify ends | M4
| Move to Azure Managed SQL PaaS |  | Replace Oracle with SQL PaaS |  | X
| Events and Notification |  | Framework readiness |  | X
|  |  | Adoption of MongoDB, Microservice Consumption Phase-1 |  |  | X
|  |  | Microservice Consumption Phase-2 |  |  |  | X
|  |  | Microservice Consumption Phase-3 |  |  |  |  | X
| Security |  | Authentication |  | X
|  |  | Authorization |  | X
|  |  | User Management |  | X
|  |  | Role Management |  |  | X
|  |  | Consent & Mandate |  |  | X
Audit
| UI/UX |  | CASA |  |  |  |  | X
|  |  | Deposits |  |  |  | X
|  |  | Customer Management |  |  |  | X
|  |  | Digital Branch |  |  |  | `
|  |  | Online Banking |  |  | X
|  |  | Lending |  |  | X
|  |  | Core |  |  |  | X
|  |  | Common Services |  |  |  |  | X
| Data Analytics and Reporting |  | Native reporting |  |  |  | X
|  |  | Adavanced analytics phase-1 |  |  |  |  | X
Adavanced analytics phase-2
|  |  | Operational Analytics |  | X
| Interfaces/integration |  | Framework readiness Product Adaptor/SPI |  | X
|  |  | Integration with Fintech/3rd Part Application Phase-1 |  |  | X
|  |  | Integration with Fintech/3rd Part Application Phase-2 |  |  |  | X
|  |  | Integration with Fintech/3rd Part Application Phase-3 |  |  |  |  | X
| Decomposition into microservices |  | CASA |  |  |  |  | X
|  |  | Deposits |  |  |  | X
|  |  | Customer Management |  |  |  | X
|  |  | Digital Branch |  |  |  | `
|  |  | Online Banking |  |  | X
|  |  | Lending |  |  | X
|  |  | Core |  |  |  | X
|  |  | Common Services |  |  |  |  | X
|  |  | Foundation Service Framework readiness |  | X
|  |  | Foundation Service Microservice Consumption |  |  | X
|  |  | Basic treasury |  |  | X
| Containerization Essence |  | Containerization Essence Phase-1 |  | X
|  |  | Containerization Essence Phase-2 |  |  | X
|  |  | Containerization Essence Phase-3 |  |  |  | X
|  |  | Containerization Essence Phase-4 |  |  |  |  | X
| QA Automation |  | QA Automation Phase-1 |  | X
|  |  | QA Automation Phase-2 |  |  | X
|  |  | QA Automation Phase-3 |  |  |  | X
|  |  | QA Automation Phase-4 |  |  |  |  | X
| Cloud Operation(CI/CD,EOD,Monitoring) |  | Autmated batch opertions Phase-1 |  | X
|  |  | Autmated batch opertions Phase-2 |  |  | X
|  |  | Autmated batch opertions Phase-3 |  |  |  | X
|  |  | Autmated batch opertions Phase-4 |  |  |  |  | X
|  |  | Business Monitoring Phase-1 |  | X
|  |  | Business Monitoring Phase-2 |  |  | X
|  |  | Business Monitoring Phase-3 |  |  |  | X
|  |  | Business Monitoring Phase-4 |  |  |  |  | X