## Posting Label
Posting Label
product | Fusion Corporate Channel
journey | Modernization
scenario | MTP
environment | Production
scoringCycle | FY 22
scoringMaturity | Draft
estimatedBy | Manikandan.g@finastra.com
estimatedOn | 21/04/2021
recordedBy | rajeshkumar.pb@finastra.com

## Sheet1
Milestones
[7 empty] | M1 | M2 | M3 | Amplify ends |  | Next Gen UX
[6 empty] | Theme |  | 1 vertical done (Trade) | 3 verticals done (+ Lending, Cash) | All verticals done (+Tsy, Supply Chain)
[6 empty] | Detail | Next-gen UX for Trade products | Next-gen UX for Lending and Cash; Microservices for Common and Trade; containerization and hosting using Kubernetes | Launch of Trade and Lending Multi tenant SaaS; Next-gen UX for Supply Chain and Treasury; Microservices for Lending and Cash (original planned modernization target state) | Extend SaaS for Cash, Supply Chain and Treasury Next-gen UX for bank users; microservices and Next-gen UX for Admin module |  | Next Gen UX for Trade Modules | 13500
[6 empty] | Date | Q4 FY21 | Q4 FY22 | Q4 FY23 | Q4 FY24 |  | Next Gen UX for Lending Modules | 4500
[12 empty] | Next Gen UX for Cash Modules | 4000
[6 empty] | Op level | 1 | 1 | 1 | 2 |  | Next Gen UX for Supply Chain Modules | 5000
UID | Big Rock | UID | Breakdown | UID | Breakdown 2 |  | M1 | M2 | M3 | Amplify ends |  | Next Gen UX for Treasury Modules | 3000
BR1 | Next-Gen UX | 1.1 | Next Gen UX for Trade Modules |  |  |  | x |  |  |  | 13500 | Next Gen UX for Admin /Middle office | 4000
|  | 1.2 | Next Gen UX for Lending Modules |  |  |  |  | x |  |  | 4500 | Next Gen UX FCC as Platform
|  | 1.3 | Next Gen UX for Cash Modules | 1.3.1 | AccountServices,Termdeposit, FundTransfer |  |  | x |  |  | 4000 | Open API | 5000
|  |  |  | 1.3.2 | Bulk,PaperInstruments,Batch |  |  | x |  |  |  | SaaS solution | 2000
|  | 1.4 | Next Gen UX for Supply Chain Modules | [5 empty] | x |  | 5000 | Cloud native and Microservices | 12000
|  | 1.5 | Next Gen UX for Treasury Modules | [5 empty] | x |  | 3000 | Customization by configuration | 4000
|  | 1.6 | Next Gen UX for Middle office | [5 empty] | x |  | 2000
|  | 1.7 | Next Gen UX for Admin | [6 empty] | x | 2000
|  | 1.8 | Next Gen UX FCC as Platform | [6 empty] | x | 3250
|  | 1.9 | Next Gen UX Enhancement | [5 empty] | x |  | 5750
BR2 | API | 2.1 | Extensions to existing APIs to support Fintech needs | [6 empty] | x | 500
|  | 2.2 | Rest APIs for Lending Next-Gen UX |  |  |  |  | x |  |  | 750
|  | 2.3 | Rest APIs for Cash Next-Gen UX |  |  |  |  | x
|  | 2.4 | New Open APIs for Trade, Cash and Lending to support Fintech needs | [6 empty] | x | 1000
|  | 2.5 | Rest APIs for Common and Trade Microservices |  |  |  |  | x |  |  | 2000
|  | 2.6 | Rest APIs for Supply Chain and Treasury Next-Gen UX | [5 empty] | x |  | 1000
|  | 2.7 | Rest APIs for Cash, Lending Microservices | [5 empty] | x |  | 600
|  | 2.8 | Rest APIs for Supply Chain and Treasury Microservices | [6 empty] | x | 400
|  | 2.9 | Rest APIs for Admin module Next gen UX and microservices | [6 empty] | x | 750
BR3 | SaaS Solution | 3.1 | Containerization and deployment using Kubernetes (On-Prem and Cloud hosting) |  |  |  |  | x |  |  | 250
|  | 3.2 | Multi-tenant support for multiple back-office systems across Trade and Lending | [5 empty] | x |  | 200
|  | 3.3 | Multi-tenant support for multiple back-office systems Cash | [6 empty] | x | 200
|  | 3.4 | Multi-tenant support for multiple back-office systems across Supply Chain and Treasury | [6 empty] | x | 200
|  | 3.5 | Optimize Test Suites for Automated Quality Gate Enforcement in CI / CD |  |  |  |  | x |  |  | 250
|  | 3.6 | Production Safe Post Deployment Health Check and Synthetic Monitoring | [5 empty] | x |  | 500
|  | 3.7 | Automated deployment to Production | [5 empty] | x |  | 100
|  | 3.8 | Multi-Tenant FCC Trade and Lending Portal SaaS | [5 empty] | x |  | 100
|  | 3.9 | Multi-Tenant FCC All module SaaS | [6 empty] | x | 200
BR4 | Cloud native and Microservices | 4.1 | Modularization of existing code to Microservice framework |  |  |  |  | x |  |  | 800
|  | 4.2 | Design completion for Microservices framework, components and bounded context |  |  |  |  | x |  |  | 1400
|  | 4.3 | Common, Audit and Trade Microservices |  |  |  |  | x |  |  | 4000
|  | 4.4 | Integration of Lookup List Microservice |  |  |  |  | x |  |  | 200
|  | 4.5 | Cash, Lending Microservices | [5 empty] | x |  | 1600
|  | 4.6 | Supply Chain and Treasury Microservices | [6 empty] | x | 2000
|  | 4.7 | Admin module Microservice | [6 empty] | x | 2000
BR5 | Customization by configuration | 5.1 | Customization by Configuration framework for Trade module |  |  |  |  | x |  |  | 1000
|  | 5.2 | Customization by Configuration framework for Lending module | [5 empty] | x |  | 750
|  | 5.2 | Customization by configuration framework for Cash | [5 empty] | x |  | 1000
|  | 5.3 | Customization by configuration framework for Supply Chain and Treasury | [6 empty] | x | 750
|  | 5.4 | Customization by configuration framework for admin module | [6 empty] | x | 500
BR6 | Account Services and Payment-FCC as Unified Digital platform | [6 empty] | x |  |  | 3200
BR7 | Cash and Channel Unification | [6 empty] | x |  |  | 4300
Note on E18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on customer feed back ux design thinking workshop