## Posting Label
Posting Label
product | Fusion Cash Management
journey | Modernization
planType | Marathon
variant | broken; explained
scenario | MTP
environment | Production
scoringCycle | FY 22
scoringMaturity | Draft
estimatedBy
estimatedOn
recordedBy

## broken explained
JourneyPlan
Big Rock | Breakdown | Breakdown 2 | Effort (md) | FY21 | FY22 | FY23 | FY24 | FY25
B2C APIs | Beneficiary |  | 800 | 240 | 560
| Payment |  | 900 |  | 900
| Other Modules |  | 2352 |  |  | 784 | 784 | 784
Cloudification – Remove Oracle Dependency |  |  | 17709 | 100 | 500 | 5703 | 5703 | 5703
Modernization – Persona Based Dashboard, Improved UI/UX |  |  | 4337 | 867 | 867 | 867 | 867 | 869
Services | Multi-Factor Manager |  | 605 | 473 | 132
| Virtual Account Manager | ARC* Recon | 1596 | 1246 | 350
|  | Account and Ledger Services | 800 |  | 800
|  | e-Wallet | 750 |  |  | 750
|  | Client Money Management | 750 |  |  | 750
|  | Escrow | 750 |  |  |  | 750
| Receivables | POC | 150 | 150
|  | Phase I | 650 |  | 650
|  | Phase II | 650 |  |  | 650
| Interbank Cash Switch | POC | 100 | 100
|  | Phase I | 475 |  | 475
|  | Phase II | 475 |  |  | 475
| Payables |  | 1995 |  |  | 600 | 1395
| Liquidity Services |  | 755 |  |  | 100 | 655
Containerization | Multi-Factor Manager |  | 50 | 50
| Virtual Account Manager |  | 75 | 75
| Cash Web Client |  | 200 |  | 200
| IRIS |  | 200 |  | 200
|  |  | 37124 | 3301 | 5634 | 10679 | 10154 | 7356