## broken explained (hidden)
Context |  | JourneyPlan
product | Fusion Cash Management | Big Rock | Breakdown | Breakdown 2 | Effort (md) | FY21 | FY22 | FY23 | FY24 | FY25
journey | Modernization | B2C APIs | Beneficiary |  | 800 | 240 | 560
|  |  | Payment |  | 900 |  | 900
|  |  | Other Modules |  | 2352
|  |  |  | Phase I |  |  |  | 784
|  |  |  | Phase II |  |  |  |  | 784
|  |  |  | Phase III | [5 empty] | 784
planType | Marathon | Cloudification – Remove Oracle Dependency |  |  | 17709
|  |  | POC |  |  | 100
|  |  | Phase I |  |  |  | 500
|  |  | Phase II |  |  |  |  | 5703
|  |  | Phase III | [5 empty] | 5703
|  |  | Phase IV | [6 empty] | 5703
variant | broken; explained | Modernization – Persona Based Dashboard, Improved UI/UX |  |  | 4337
|  |  | Widgets |  |  | 867
|  |  | Phase I |  |  |  | 867
|  |  | Phase II |  |  |  |  | 867
|  |  | Phase III | [5 empty] | 867
|  |  | Phase IV | [6 empty] | 869 | 18 | 144
scenario | Default | Services | Multi-Factor Manager |  | 605 | 473 | 132 |  |  |  |  | 432
environment | Product Forward Branch |  | Virtual Account Manager | ARC* Recon | 1596 | 1246 | 350
scoringCycle |  |  |  | Account and Ledger Services | 800 |  | 800
scoringMaturity | Draft |  |  | e-Wallet | 750 |  |  | 750
estimatedBy |  |  |  | Client Money Management | 750 |  |  | 750
estimatedOn |  |  |  | Escrow | 750 |  |  |  | 750
recordedBy |  |  | Receivables | POC | 150 | 150
|  |  |  | Phase I | 675 |  |  | 675
|  |  |  | Phase II | 675 |  |  |  | 675
|  |  | Interbank Cash Switch | Phase I | 532 | 532
|  |  |  | Phase II | 490 |  | 490
|  |  |  | Phase III | 490 |  |  | 490
|  |  | Payables |  | 1995 |  |  | 600 | 1395
|  |  | Liquidity Services |  | 1255 |  |  | 100 | 655 | 500
|  | Containerization | Multi-Factor Manager |  | 50 | 50
|  |  | Virtual Account Manager |  | 75 | 75
|  |  | Cash Web Client |  | 200 |  | 200
|  |  | IRIS |  | 200 |  | 200
[5 empty] | 38136 | 3733 | 4999 | 10719 | 10829 | 7856

## Sheet1 (hidden)
Context |  | JourneyPlan
product | Fusion Cash Management | Big Rock | Breakdown | Breakdown 2 | Effort (md) | FY21 | FY22 | FY23 | FY24 | FY25
journey | Modernization | B2C APIs | Beneficiary |  | 800 | 240 | 560
|  |  | Payment |  | 900 |  | 900
|  |  | Other Modules |  | 2352
|  |  |  | Phase I |  |  |  | 784
|  |  |  | Phase II |  |  |  |  | 784
|  |  |  | Phase III | [5 empty] | 784
planType | Marathon | Cloudification – Remove Oracle Dependency |  |  | 17709
|  |  | POC |  |  | 100
|  |  | Phase I |  |  |  | 500
|  |  | Phase II |  |  |  |  | 5703
|  |  | Phase III | [5 empty] | 5703
|  |  | Phase IV | [6 empty] | 5703
variant | broken; explained | Modernization – Persona Based Dashboard, Improved UI/UX |  |  | 4337
|  |  | Widgets |  |  | 867
|  |  | Phase I |  |  |  | 867
|  |  | Phase II |  |  |  |  | 867
|  |  | Phase III | [5 empty] | 867
|  |  | Phase IV | [6 empty] | 869 | 18 | 144
scenario | Default | Services | Multi-Factor Manager |  | 605 | 473 | 132 |  |  |  |  | 432
environment | Product Forward Branch |  | Virtual Account Manager | ARC* Recon | 1596 | 1246 | 350
scoringCycle |  |  |  | Account and Ledger Services | 800 |  | 800
scoringMaturity | Draft |  |  | e-Wallet | 750 |  |  | 750
estimatedBy |  |  |  | Client Money Management | 750 |  |  | 750
estimatedOn |  |  |  | Escrow | 750 |  |  |  | 750
recordedBy |  |  | Receivables | POC | 150 | 150
|  |  |  | Phase I | 675 |  |  | 675
|  |  |  | Phase II | 675 |  |  |  | 675
|  |  | Interbank Cash Switch | Phase I | 532 | 532
|  |  |  | Phase II | 490 |  | 490
|  |  |  | Phase III | 490 |  |  | 490
|  |  | Payables |  | 1995 |  |  | 600 | 1395
|  |  | Liquidity Services |  | 1255 |  |  | 100 | 655 | 500
|  | Containerization | Multi-Factor Manager |  | 50 | 50
|  |  | Virtual Account Manager |  | 75 | 75
|  |  | Cash Web Client |  | 200 |  | 200
|  |  | IRIS |  | 200 |  | 200
|  |  |  | Total | 38136 | 3733 | 4999 | 10719 | 10829 | 7856
|  |  |  | Modernization | Effort (md) | FY21 | FY22 | FY23 | FY24 | FY25
|  |  |  | Total | 38136 | 3733 | 4999 | 10719 | 10829 | 7856
|  |  |  | Yearly Working Days |  | NA | 216 | 216 | 216 | 216
|  |  |  | No of Resources |  | NA | 23.1435 | 49.625 | 50.1343 | 36.3704
|  |  |  | Product Investments |  | FY21 | FY22 | FY23 | FY24 | FY25
|  |  |  | Product L3/IMPL Support |  |  | 47 | 47 | 47 | 47
|  |  |  | HDFC-RA |  |  | 9 | 9
|  |  |  | ECO-RA |  |  | 5 | 5 | 5 | 5
|  |  |  | HBL-RA |  |  | 4
|  |  |  | Mizuho -RF |  |  | 3 | 3 | 3 | 3
|  |  |  | UAB Enhancements |  |  | 2
|  |  |  | Quality - Test Case Automation |  |  | 10 | 8 | 6 | 4
|  |  |  | Technical debt |  |  | 2 | 2 | 2 | 2
|  |  |  | FCM - Mobile Enhancements |  |  | 3.2 | 3.2 | 3.2 | 3.2
|  |  |  | Management |  |  | 14.5 | 14.5 | 14.5 | 14.5
|  |  |  | Total Resources |  |  | 99.7 | 91.7 | 80.7 | 78.7
|  |  |  | Resource Requirement |  | FY21 | FY22 | FY23 | FY24 | FY25
|  |  |  | Grand Total |  |  | 122.8435 | 141.325 | 130.8343 | 115.0704
|  |  |  | Avaiable Resources |  |  | 117 | 117 | 117 | 117
|  |  |  | Variance |  |  | -5.8435 | -24.325 | -13.8343 | 1.9296
|  |  |  | Avg Resource Requirement | 11

## Posting Label
Postinh Label
product | Fusion Cash Management
journey | Modernization
planType | Marathon
variant | broken; explained
scenario | MTP
environment | Production
scoringCycle | FY 22
scoringMaturity | Draft
estimatedBy
estimatedOn | 2021-06-08
recordedBy

## broken explained-Revised
JourneyPlan
Big Rock | Breakdown | Breakdown 2 | Effort (md) | FY21 | FY22 | FY23 | FY24 | FY25
B2C APIs | Beneficiary |  | 800 | 240 | 560
| Payment |  | 900 |  | 900
| Other Modules |  | 2352
|  | Phase I |  |  |  | 784
|  | Phase II |  |  |  |  | 784
|  | Phase III | [5 empty] | 784
Cloudification – Remove Oracle Dependency |  |  | 600
| POC |  |  | 100
| Remove Reports Dependency Removal |  |  |  | 500
Modernization – Persona Based Dashboard, Improved UI/UX |  |  | 4337
| Widgets |  |  | 867
| Phase I |  |  |  | 867
| Phase II |  |  |  |  | 867
| Phase III | [5 empty] | 867
| Phase IV | [6 empty] | 869
Services | Multi-Factor Manager |  | 605 | 473 | 132
| Virtual Account Manager | ARC* Recon | 1596 | 1246 | 350
|  | Account and Ledger Services | 800 |  | 800
|  | e-Wallet | 750 |  |  | 750
|  | Client Money Management | 750 |  |  | 750
|  | Escrow | 750 |  |  |  | 750
| Receivables | POC | 150 | 150
|  | Phase I | 675 |  |  | 675
|  | Phase II | 675 |  |  |  | 675
| Interbank Cash Switch | Phase I | 532 | 532
|  | Phase II | 490 |  | 490
|  | Phase III | 490 |  |  | 490
| Payables | Phase I | 600 |  |  | 600
|  | Phase II | 1395 |  |  |  | 1395
| Liquidity Services |  | 1255 |  |  | 100 | 655 | 500
Containerization | Multi-Factor Manager |  | 50 | 50
| Virtual Account Manager |  | 75 | 75
| Cash Web Client |  | 200 |  | 200
| IRIS |  | 200 |  | 200
|  | Total | 21027 | 3733 | 4999 | 5016 | 5126 | 2153