## Posting Label
Posting Label
product | Fusion Cash Management
journey | Modernization
scenario | MTP
environment | Production
scoringCycle | FY 22
scoringMaturity | Draft
estimatedBy
estimatedOn | 2021-06-10
recordedBy

## FCM
Milestones
[7 empty] | FY22 | FY23 | FY24 | FY25
[6 empty] | Theme | CaaS 50%; containerization; 15% of planned microservices transformation | CaaS 100%; 60% of planned microservices transformation | Receivable microservices | continuously improvement of UI/UX and API; reduction of Oracle tech debt
[6 empty] | Detail | Cash as Service - (Interbank Cash Switch, Cash Lite) Virtual Account Management (ARC Recon, Interbank Cash Switch, Account & Ledger Services), B2C, B2B APIs; Containerization; Reduce Oracle Dependency | Cash as Service - (Interbank Cash Switch, Cash Lite) Virtual Account Management (eWallet, Client Money Management); Receivables Service; Payment Service; B2C APIs; Reduce Oracle Dependency | Cash as Service - Virtual Account Management (Escrow), Receivable Service; Payment Service; Liquidity Services; Reduce Oracle Dependency; B2C APIs; UI/UX | Reduce Oracle Dependency; B2C APIs; UI/UX
[6 empty] | Date | FY22-Q4 | FY23-Q4 | FY24-Q4 | FY25-Q4
Op level
UID | Big Rock | UID | Breakdown | UID | Breakdown 2 |  | M1 | M2 | M3 | M4
BR1 | B2C APIs
|  | 1.1 | Beneficiary API |  |  |  | x
|  | 1.2 | Payment API |  |  |  | x
|  | 1.3 | Others
|  |  |  | 1.3.1 | Phase I |  |  | x
|  |  |  | 1.3.2 | Phase II |  |  |  | x
|  |  |  | 1.3.3 | Phase III |  |  |  |  | x
BR2 | Cloudification – Remove Oracle Dependency
|  | 2.1 | Phase I |  |  |  | x
|  | 2.2 | Phase II |  |  |  |  | x
BR3 | Modernization – Persona Based Dashboard, Improved UI/UX
|  | 3.1 | Phase I |  |  |  | x
|  | 3.2 | Phase II |  |  |  |  | x
|  | 3.3 | Phase III | [5 empty] | x
|  | 3.4 | Phase IV | [6 empty] | x
BR4 | Services
|  | 4.2 | Virtual Account Manager | 4.2.1 | ARC* Recon |  | x
|  |  |  | 4.2.2 | Account and Ledger Services |  | x
|  |  |  | 4.2.3 | e-Wallet |  |  | x
|  |  |  | 4.2.4 | Client Money Management |  |  | x
|  |  |  | 4.2.5 | Escrow |  |  |  | x
|  | 4.3 | Receivables | 4.3.1 | Phase I |  |  | x
|  |  |  | 4.3.2 | Phase II |  |  |  | x
|  | 4.4 | Interbank Cash Switch | 4.4.1 | Phase II |  | x
|  |  |  | 4.4.2 | Phase III |  |  | x
|  | 4.5 | Payables | 4.5.1 | Phase I |  |  | x
|  |  |  | 4.5.2 | Phase II |  |  |  | x
|  | 4.6 | Liquidity Services | [6 empty] | x
BR5 | Containerization | 5.1 | Cash Web Client |  |  |  | x
|  | 5.2 | IRIS |  |  |  | x