## Posting Label
Posting Label
product | Fusion GPP
journey | Modernization
scenario | MTP
environment | Production
scoringCycle | FY 22
scoringMaturity | Draft
estimatedBy | shai.kopelman@finastra.com
estimatedOn | 2021-06-08
recordedBy | alexander.troyanovsky@finastra.com

## GPP Plan
Milestones
[7 empty] | M1 | M2 | M3 | M4 | M5 (QBR reported) | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | Target State
[6 empty] | Theme | Containerized Monolith | Kafka as mandatory component | Archiving (phase I) and improved search | MongoDB replacing Oracle Enterprise (+XA elimination) | Full Oracle decomission (introduction of PG) | Full adoption of modernized file ingestion | Complete interface migration to GW (Integration via SPI) | multi-cloud (AWS) Product certification | FO monitoring, logging, tracing adoption | Tactical replacement of internal IBM MQ with ActiveMQ | Archiving (phase II) | Fully multitenant GPP | FO Service Ops Model adoption - assuming Hybrid deployment (Monolith and MS) | Complete essential openapis | Decomission App Server | Decomission Internal ActiveMQ
[6 empty] | Date | v21 (27/12/21) | V20 (13/9/21) | V20 (13/9/21) | V25 (8/11/22) | V27 (June, 2023) |  | V25 (8/11/22) | V22 (11/4/22) | V23 (25/7/22) |  | V24 (7/11/22) | V30 (April-2024) | V23 (25/7/22) | V23 (25/7/22) | V30 (April-2024) |  | 2024-04-01
Op level
UID | Big Rock | UID | Breakdown | UID | Breakdown 2 |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16
| MS Infrastructure | [21 empty] | x
| Oracle Elimination |  | MongoDB for transactional data | bar: M4
PG for config/reference data | bar: M5
| MicroServices |  | Decomission AppServer | bar: M15
full multi-tenancy | bar: M12
AWS | bar: M8
| File Processing |  | file ingestion | bar: M6
|  |  | file generation | [19 empty] | x
| Security |  | Security Haedening | [19 empty] | x
|  |  | Data at Rest / In transit | [19 empty] | x
| UI/UX |  | Multi tenant login | [19 empty] | x
|  |  | User Preferences MS? | [19 empty] | x
| Interfaces over GW (SPI) |  | Kafka | bar: M2
|  |  | Decomission IBM MQ |  | phase I | bar: M10
phase II | bar: M16
SPIs over GW | bar: M7
| Containerization and FO Adoption |  | Containerized monolith | bar: M1
FO Obesrvabilty | bar: M9
FO SOM | bar: M13
Open API | bar: M14
| Data |  | Kafka | bar: M2
|  |  | Archiving |  | phase I | bar: M3
phase II | bar: M11