## Posting Label
Posting Label
product | Loan IQ
journey | Modernization
planType | Marathon
variant | simple; burnout
scenario | MTP
environment | Production
scoringCycle | FY 22
scoringMaturity | Draft
estimatedBy | krishna.tikkisetty@finastra.com
estimatedOn | 2021-03-06
recordedBy | krishna.tikkisetty@finastra.com

## LIQ
Milestones
[7 empty] | M1 | M2
Theme
[6 empty] | Detail | Continue Enhancing LIQ Ecosystem for SME market, Cloud journey, OpenBanking and Improving Customer Experience | Continue Enhancing LIQ Ecosystem for SME market, Improving Customer Experience
[6 empty] | Date | Q4'22 | Q4'23
Op level
UID | Big Rock | UID | Breakdown | UID | Breakdown 2 |  | M1 | M2
BR1 | Web Browser UI/UX on UXP | 1.1 | SME Servicing |  |  |  | x
|  | 1.2 | Syndicated servicing |  |  |  |  | x
|  | 1.3 | Web client Essentials - 763 |  |  |  | x
|  | 1.4 | Booking Services |  |  |  | x
BR2 | Containerization | 2.1 | Container Guideines in linux
|  |  |  | 2.1.1 | MVP1 |  | x
|  |  |  | 2.1.2 | MVP2 |  |  | x
BR3 | EDB PostGreSQL Stabilization | [5 empty] | x
BR4 | FFDC Open APIs
|  | 4.1 | ARR calculator |  |  |  | x
|  | 4.2 | FO Migration |  |  |  | x
|  | 4.3 | Syndication Primaries |  |  |  | x
|  | 4.4 | Booking Origination |  |  |  | x
|  | 4.5 | E2E LIQ-Sales on Salesforce |  |  |  | x
BR5 | Application Server System
|  | 5.1 | Extended Capabilities
|  |  |  | 5.1.1 | MVP1 |  | x
|  |  |  | 5.1.2 | MVP2 |  |  | x
|  | 5.2 | Transformation |  |  |  |  | x