## simple burnout
Posting Label |  | JourneyPlan |  | JourneyInvestment
product | LaserPro | Big Rock | Effort (md) | Period | Incremental | Cumulative
journey | Modernization | UI/UX Dynamic Rendering | 500 | FY 2021 | 3120 | 3120
planType | Marathon | Refactor Core UI Screens | 500 | FY 2022 | 3120 | 6240
variant | simple; burnout | Containerization, Routing, Security | 500 | FY 2023 | 820 | 7060
scenario |  | Operate in FusionOperate | 500 | FY 2024 |  | 7060
environment | Production | Dynamic Provisioning | 500 | FY 2025 |  | 7060
scoringCycle | Dec 2020 | Cloud Management APIs | 240
scoringMaturity | Draft | Enable Multi-tenant database (post process) | 120
estimatedBy | paul.imel@finastra.com | Enable Multi-tenant database (naitive) | 500
estimatedOn | 2021-05-25 | Integration with Lending Services | 500
recordedBy | mike.lucas@finastra.com | FFDC Data Cloud Integration | 500
|  | FFDC Messaging Integration | 500
|  | FFDC Intragtion APIs (SPIs) | 500
|  | FFDC Open APIs for FinTechs | 500
|  | Core Solutions Integration | 1200
7060

## broken burnout
Posting Label |  | JourneyPlan |  |  |  | JourneyInvestment
product | LaserPro | Big Rock | Breakdown | Breakdown 2 | Effort (md) | Period | Incremental | Cumulative
journey | Modernization | UI/UX Dynamic Rendering | Controls |  | 100 | FY 2021 | 3120 | 3120
planType | Marathon |  | Document Display / Printing |  | 100 | FY 2022 | 3120 | 6240
variant | broken; burnout |  | Validation |  | 100 | FY 2023 | 820 | 7060
scenario |  |  | Automated Testing |  | 100 | FY 2024 |  | 7060
environment | Production |  | Styling |  | 100 | FY 2025 |  | 7060
scoringCycle | Dec 2020 | Refactor Core UI Screens |  |  | 500
scoringMaturity | Draft | Containerization, Routing, Security | Containerization |  | 100
estimatedBy | paul.imel@finastra.com |  | Routing |  | 300
estimatedOn | 2021-05-25 |  | Route/Pod Security |  | 100
recordedBy | mike.lucas@finastra.com | Operate in FusionOperate | Onboard APIs & Team to FO Repo |  | 200
|  |  | Integrate Monitoring |  | 200
|  |  | Onboard .NET 4.8 Project/Pipeline |  | 100
|  | Dynamic Provisioning | k8s Operator |  | 300
|  |  | Storage Binding |  | 100
|  |  | Version Selector |  | 100
|  | Cloud Management APIs | Licensing API |  | 80
|  |  | Session API |  | 80
|  |  | Administration API |  | 80
|  | Enable Multi-tenant database (post process) | File Watch ETL Service |  | 120
|  | Enable Multi-tenant database (naitive) |  |  | 500
|  | Integration with Lending Services |  |  | 500
|  | FFDC Data Cloud Integration |  |  | 500
|  | FFDC Messaging Integration |  |  | 500
|  | FFDC Intragtion APIs (SPIs) |  |  | 500
|  | FFDC Open APIs for FinTechs |  |  | 500
|  | Core Solutions Integration |  |  | 1200
7060

## simple explained
Posting Label |  | JourneyPlan
product | LaserPro | Big Rock | Effort (md) | FY21 | FY22 | FY23 | FY24 | FY25
journey | Modernization | UI/UX Dynamic Rendering | 500 | 500
planType | Marathon | Refactor Core UI Screens | 500 | 500
variant | simple; explained | Containerization | 500 | 500
scenario |  | Operate in FusionOperate | 500 | 500
environment | Production | Dynamic Provisioning | 500 | 500
scoringCycle | Dec 2020 | Cloud Management APIs | 240 | 240
scoringMaturity | Draft | Enable Multi-tenant database (post process) | 120 | 120
estimatedBy | paul.imel@finastra.com | Enable Multi-tenant database (naitive) | 500 |  |  | 500
estimatedOn | 2021-05-25 | Integration with Lending Services | 500 | 260 | 240
recordedBy | mike.lucas@finastra.com | FFDC Data Cloud Integration | 500 |  | 500
|  | FFDC Messaging Integration | 500 |  | 500
|  | FFDC Intragtion APIs (SPIs) | 500 |  | 500
|  | FFDC Open APIs for FinTechs | 500 |  | 500
|  | Core Solutions Integration | 1200 |  | 880 | 320
|  |  | 7060 | 3120 | 3120 | 820 | 0 | 0

## broken explained
Posting Label |  | JourneyPlan
product | LaserPro | Big Rock | Breakdown | Breakdown 2 | Effort (md) | FY21 | FY22 | FY23 | FY24 | FY25
journey | Modernization | UI/UX Dynamic Rendering | Controls |  | 100 |  | 100
planType | Marathon |  | Document Display / Printing |  | 100 |  | 100
variant | broken; explained |  | Validation |  | 100 |  | 100
scenario |  |  | Automated Testing |  | 100 |  | 100
environment | Production |  | Styling |  | 100 |  | 100
scoringCycle | Dec 2020 | Refactor Core UI Screens |  |  | 500 |  | 500
scoringMaturity | Draft | Containerization, Routing, Security | Containerization |  | 100 |  | 100
estimatedBy | paul.imel@finastra.com |  | Routing |  | 300 |  | 300
estimatedOn | 2021-05-25 |  | Route/Pod Security |  | 100 |  | 100
recordedBy | mike.lucas@finastra.com | Operate in FusionOperate | Onboard APIs & Team to FO Repo |  | 200 |  | 200
|  |  | Integrate Monitoring |  | 200 |  | 200
|  |  | Onboard .NET 4.8 Project/Pipeline |  | 100 |  | 100
|  | Dynamic Provisioning | k8s Operator |  | 300 |  | 300
|  |  | Storage Binding |  | 100 |  | 100
|  |  | Version Selector |  | 100 |  | 100
|  | Cloud Management APIs | Licensing API |  | 80 |  | 80
|  |  | Session API |  | 80 |  | 80
|  |  | Administration API |  | 80 |  | 80
|  | Enable Multi-tenant database (post process) | File Watch ETL Service |  | 120 |  | 120
|  | Enable Multi-tenant database (naitive) |  |  | 500 |  |  |  | 500
|  | Integration with Lending Services |  |  | 500 |  | 260 | 240
|  | FFDC Data Cloud Integration |  |  | 500 |  |  | 500
|  | FFDC Messaging Integration |  |  | 500 |  |  | 500
|  | FFDC Intragtion APIs (SPIs) |  |  | 500 |  |  | 500
|  | FFDC Open APIs for FinTechs |  |  | 500 |  |  | 500
|  | Core Solutions Integration |  |  | 1200 |  |  | 880 | 320
[5 empty] | 7060 | 0 | 3120 | 3120 | 820 | 0