## Sheet1
Posting Label | [7 empty] | Milestones
product | LaserPro | [7 empty] | M1 | M2 | Amplify ends | M4 | Target State
journey | Modernization | [6 empty] | Theme | Cloud MVP for early adopters | Complete APIs and FFDC Service Integration | Reduce Cloud Complexity
[8 empty] | Date | Q3 FY22 | Q2 FY 23 | Q4 FY 24 | Q4 FY 25
scenario |  | UID | Big Rock | UID | Breakdown | UID | Breakdown 2 |  | M1 | M2 | Amplify ends | M4
environment | Production | BR1 | UI/UX Dynamic Rendering | 1.1 | Controls |  |  |  | x
scoringCycle | Dec 2020 |  |  | 1.2 | Document Display / Printing |  |  |  | x
scoringMaturity | Draft |  |  | 1.3 | Validation |  |  |  | x
estimatedBy | paul.imel@finastra.com |  |  | 1.4 | Automated Testing |  |  |  | x
estimatedOn | 2021-05-25 |  |  | 1.5 | Styling |  |  |  | x
recordedBy | mike.lucas@finastra.com | BR2 | Refactor Core UI Screens | [5 empty] | x
|  | BR3 | Containerization, Routing, Security | 3.1 | Containerization |  |  |  | x
|  |  |  | 3.2 | Routing |  |  |  | x
|  |  |  | 3.3 | Route/Pod Security |  |  |  | x
|  | BR4 | Operate in FusionOperate | 4.1 | Onboard APIs & Team to FO Repo |  |  |  | x
|  |  |  | 4.2 | Integrate Monitoring |  |  |  | x
|  |  |  | 4.3 | Onboard .NET 4.8 Project/Pipeline |  |  |  | x
|  | BR5 | Dynamic Provisioning | 5.1 | k8s Operator |  |  |  | x
|  |  |  | 5.2 | Storage Binding |  |  |  | x
|  |  |  | 5.3 | Version Selector |  |  |  | x
|  | BR6 | Cloud Management APIs | 6.1 | Licensing API |  |  |  | x
|  |  |  | 6.2 | Session API |  |  |  | x
|  |  |  | 6.3 | Administration API |  |  |  | x
|  | BR7 | Enable Multi-tenant database (post process) |  | File Watch ETL Service |  |  |  | x
|  | BR8 | Enable Multi-tenant database (naitive) | [6 empty] | x
|  | BR9 | Integration with Lending Services | [7 empty] | x
|  | BR10 | FFDC Data Cloud Integration | [6 empty] | x
|  | BR11 | FFDC Messaging Integration | [6 empty] | x
|  | BR12 | FFDC Intragtion APIs (SPIs) | [6 empty] | x
|  | BR13 | FFDC Open APIs for FinTechs | [6 empty] | x
|  | BR14 | Core Solutions Integration | [7 empty] | x