## Posting Label
Posting Label
product | OPICS
journey | Modernization
scenario | MTP
environment | Production
scoringCycle | FY 22
scoringMaturity | Draft
estimatedBy | gopinath.annaji@finastra.com
estimatedOn | 2021-06-08
recordedBy | gopinath.annaji@finastra.com

## OPICS
Milestones
[7 empty] | FY22 P1 | FY22 P2 | FY22 P3 | FY22 P4 | FY23 P1 (M1) | FY23 P2 | FY22 P3 | FY23 P4 (M2) | Target State | Nb of X's
[6 empty] | Theme |  |  |  |  | 50% shorter release cycles |  |  | CAM expands in Tier 4/5 via TCO reduction
[6 empty] | Details | UX Synchronization, Test automation, Azure Bus, STS to .NET 5 | Express static UXP, Cloud monitoring, API standardization | UXP upgrade, WCF to .NET 5 | Upgraded UXP with better security and performance and standardization of FX, CN API | OPEN RDBMS support | APIM support, CI maturity, Windows service to .NET | ADMIN screens in UXP | Support Multi-platform for Express instruments via Linux which reduces infracture cost at least 30% | Finish up migration for UX, Robot, and Linux
[6 empty] | Date | Q1FY22 | Q2 FY22 | Q3FY22 | Q4FY22 | Q1FY23 | Q2FY23 | Q3FY23 | Q4FY23 | Q4FY25
[7 empty] | 2021-08-22 | 2021-11-21 | 2022-02-22 | 2022-05-22 | 2022-08-01 | 2022-11-01 | 2023-01-01 | 2023-05-01
Op level
UID | Big Rock | UID | Breakdown | UID | Breakdown 2 |  | FY22 P1 | FY22 P2 | FY22 P3 | FY22 P4 | FY23 P1 | FY23 P2 | FY22 P3 | FY23 P4 | Target State
| Modernize UX - web application |  | UXP upgrade | [12 empty] | 1 | bar: 2022-02-22
|  |  | Static Screen enablement | [12 empty] | 1 | bar: 2021-11-21
|  |  | UXP gaps in FX/DL/FI/REPO/IRS | [12 empty] | 1 | bar: 2021-08-22
|  |  | Admin screens | [12 empty] | 2 | bar: 2022-11-01 to 2023-01-01
|  |  | UXP performance testing | [12 empty] | 1 | bar: 2022-05-22
|  |  | UXP Security Testing | [12 empty] | 1 | bar: 2022-05-22
|  |  | UXP support for other instruments | [11 empty] | x | 3 | bar: 2022-11-01 to 2023-05-01
0
| API as a Product |  | API versioning & APIM support | [12 empty] | 1 | bar: 2022-11-01
|  |  | API performance testing | [12 empty] | 1 | bar: 2022-05-22
0
| Cloud Operating |  | Monitoring maturity | [12 empty] | 1 | bar: 2021-11-21
|  |  | High availability testing | [12 empty] | 1 | bar: 2022-05-22
|  |  | Service Update - Evergreening | [12 empty] | 1 | bar: 2022-11-01
|  |  | CI Maturity |  | Quality Gates maturity | [10 empty] | 4 | bar: 2021-11-21 to 2022-05-22; 2023-05-01
[5 empty] | MTAF to ROBOT migration - phase 1 | [10 empty] | 5 | bar: 2021-08-22 to 2022-08-01
MTAF to ROBOT migration - Phase 2 | bar: 2022-11-01 to 2023-05-01
[5 empty] | MTAF to ROBOT migration - phase 3 | [9 empty] | x
|  |  | Docker Maturity |  | Open Shift support | [10 empty] | 2 | bar: 2022-02-22 to 2022-05-22
0
| Data as a Product |  | Data sharing for Cloud Margin | [12 empty] | 1 | bar: 2021-11-21
|  |  | Extend data sharing for Fincad | [12 empty] | 1 | bar: 2022-02-22
0
| Strangle and Simplify |  | Azure Bus support | [12 empty] | 1 | bar: 2021-08-22
|  |  | OPEN SQL support (RDBMS) | [12 empty] | 3 | bar: 2022-11-01 to 2023-05-01
0
| FFDC standard |  | API Standardization | [12 empty] | 4 | bar: 2021-11-21 to 2022-08-01
|  |  | API Standardization - phase 2 | [12 empty] | 3 | bar: 2022-11-01 to 2023-05-01
0
| Multi platform support |  | .NET migration |  | WCF migration | [10 empty] | 3 | bar: 2021-08-22 to 2022-02-22
[5 empty] | WF migration - framework | [10 empty] | 2 | bar: 2022-02-22 to 2022-05-22
WF migration - Pubsub and Reval | bar: 2022-08-01 to 2022-11-01
Windows services migration - Framework | bar: 2022-05-22 to 2022-08-01
[5 empty] | Windows services migration | [10 empty] | 3 | bar: 2022-11-01 to 2023-05-01
[5 empty] | .NET client | [10 empty] | 3 | bar: 2022-11-01 to 2023-05-01
[5 empty] | Packaging and deployment | [10 empty] | 2 | bar: 2022-02-22 to 2022-05-22
[5 empty] | Confirmations support | [10 empty] | 1 | bar: 2023-05-01
[5 empty] | Code migration - phase 1 | [10 empty] | 3 | bar: 2022-11-01 to 2023-05-01
[5 empty] | Code migration - phase 2 | [9 empty] | x | 0