## Posting Label
Posting Label
product | Fusion Phoenix
journey | Modernization
planType | Marathon
variant | broken; explained
scenario
environment | Production
scoringCycle | Dec 2020
scoringMaturity | Draft
estimatedBy | Ashok, Milind, Aaron and John
estimatedOn | 2021-05-22
recordedBy | ashok.ramakrishnan@finastra.com

## broken explained
JourneyPlan
Big Rock | Breakdown | Breakdown 2 | Effort (md) | FY22 | FY23
BaaS -Banking as a Service |  |  | 0
| Simple personal Customer, Deposit Checking, Installment Loan Onboarding |  | 100 | 100
| BaaS - Virtual customers and accounts - Assessment |  | 10 | 10
| Google Plex - Events engine - v1 |  | 50 | 50
| Google Plex - Cards - API wrapper to add cards in Phoenix |  | 50 | 50
| Google Plex - Generic changes |  | 100 | 100
| Google Plex - Separate Phoenix instance impact analysis |  | 10 | 10
| New Branch model in Phoenix - Fintech access |  | 100 |  | 100
| PCI: SQL Injection | Phase 1 - Satisfies Google Plex PCI Requirements(Delivered in Branch) | 570 | 570
|  | Phase 2 - Satisfies entire Phoenix codeline | 800 | 800
| PCI Assessment - Separare Phoenix Instance for Google Plex - Encryption key mgmt changes |  | 50 | 50
| API's: Commercial and other personas | API Phase 1: Commercial and other personas | 200 | 200
|  | API Phase 2: Commercial and other personas | 150 |  | 150
| Events engine - v2 - All Fintechs |  | 150 | 150
| Cards - Integration with FIS Payments 1 | Cards - Create card in Phx- FFDC - Payment One SPI (FFDC Team) | 0
|  | Real-time Integration - New cards - FFDC SPI to Payments 1 | 100 | 100
|  | Real-time Integration - Hot cards - FFDC SPI to Payments 1 | 50 | 50
|  | Card management - Addr, acct change- FFDC SPI to Payments 1 | 50 |  | 50
Cloud Enablement |  |  | 0
| UpSkilling for BaaS and Cloud Enablement |  | 100 | 100
| Monitoring | Monitoring - Phase 1 - Infrastructure and throughout monitoring without dev changes | 10 | 10
|  | Monitoring - Phase 2 - monitoring with dev changes to provide correlation and flow tracking for MTTR | 100 |  | 100
| Containerization | Phoenix REST | 500 | 500
|  | PhoeniXM SOAP | 200 | 200
| Headless Nigthly | Create Plan | 10 | 10
|  | Headless Nightly Phase 1 (Copy Over and Back for upgrades) | 150 |  | 150
|  | Headless Nightly Phase 2 | 623 |  | 623
|  | Headless Nightly Reports | 100 |  | 100
| Nigthly Reports | Conversion to C# - Performance improvement - Batch 1 | 585 | 585
|  | Conversion to C# - Performance improvement - Batch 2 | 600 | 600
|  | Conversion to C# - Performance improvement - Batch 3 | 400 |  | 400
| Cloud Database- SQL Hyperscale | Assesment | 50 | 50
|  | Hyperscale -Phase 1 | 100 | 100
|  | Hyperscale -Phase 1 | 700 |  | 700
| Supportability | Log Aggregation - Phase 1- REST API's | 100 | 100
|  | Log Aggregation - Phase 2 - SOAP APIs and improved logging | 100 |  | 100
| Operations-Optimizations | Implement additional file loads via APIs -REST | 150 |  | 150
| Phoenix Benchmarking and changes |  | 300 |  | 300
GS Improvements | Legacy Migration - Ultradata generic data extract to improve efficiency of legacy migrations |  | 150 | 150
| Product enhancements - Improve GS efficiency in Phoenix deployment |  | 150 |  | 150
UI/UX | UI/UX Assesment |  | 50 | 50
| Explore cloud deployment of existing U |  | 50 | 50
| Persona 1 with New UI/UX |  | 1300 |  | 1300
Product Enhancements | Card Payments -ISO Integration | Build - ISO Integration - Replace InterPRO - Assessment | 0
|  | Build - ISO Integration - Replace InterPRO | 750 |  | 750
|  | Recurring Maintainence - ISO Integration - Every half FY | 480 |  | 480
|  |  | 10348 | 4745 | 5603