## Posting Label
Posting Label
product | Fusion Summit
journey | Modernization
scenario | MTP
environment | Production
scoringCycle | FY 22
scoringMaturity
estimatedBy
estimatedOn
recordedBy

## Sheet1
Milestones
[5 empty] | M1 | M2 | M3 (Amplify ends) | M4 | Target State
|  |  |  | Theme | First phase of improving managed hosted cloud operability and benefits from cloud deployment ( scalability and HA ) | First round of microsevices and UX improvements | REST-enabled system with extended UX capabilities | Continue microservices on demand.
|  |  |  | Date | Q4 FY22 | Q4 FY 23 | Q4 FY 24 | Q4 FY 25
CAM $
Op level
UID | Big Rock | UID | Breakdown |  | M1 | M2 | Amplify ends | M4
BR1 | Cloud operating model | 1.1 | Solution wide Configuration management & Service discovery |  | x
|  | 1.2 | Solution wide Orchestration monitoring and health check (open tracing, etc) |  |  |  | X
|  | 1.3 | Azure SQL database |  | x
|  | 1.4 | Automation for development operations |  |  | X
BR2 | Rest API | 2.1 | Performance - outbound APIs (Read) |  | x
|  | 2.2 | Client SDK for REST interface extendibility |  |  | X
|  | 2.3 | Inbound interface through REST (Write + STD Action) |  |  |  | X
|  | 2.4 | Inbound performance/Parallel writes |  |  |  | X
BR3 | Functional REST API | 3.1 | Market data |  | x
|  | 3.2 | Curve generation |  |  |  | x
|  | 3.3 | risk management |  |  | x
|  | 3.4 | position management APIs |  |  |  | x
|  | 3.5 | Settlement affirmation |  |  | x
BR4 | Decomposition to microservices | 4.1 | Microservice for curve generation using Summit core functionality |  |  |  | X
|  | 4.2 | Microservice for collateral connectivity |  |  | X
|  | 4.3 | Microservice for trade affirmation |  |  |  | X
BR5 | Scalability & HA | 5.1 | Sequencer: deployment, performance/stress testing |  | x
|  | 5.2 | Config management server |  | x
|  | 5.3 | FT Middle + ETKWS + Springboot (axis2 out) + WS |  |  |  | X
|  | 5.4 | Load balancing (STP, ETK) |  |  | X
|  | 5.5 | API Gateway |  | x
|  | 5.6 | ASB / additional JMS providers |  |  |  | X
BR6 | UX capabilities extension | 6.1 | Extend to equities position manager |  | x
|  | 6.2 | Workflow for pre-deal trade management |  |  |  | X
|  | 6.3 | UXP upgrade |  |  | X
BR7 | Streamlining upgrades | 7.1 | Customer extensions on Kubernetes deployment |  | x
BR8 | FFDC selected APIs | 8.1 | Enablement for inbound interfaces for trades import. |  |  | x
|  | 8.2 | Enablement for risk and positions management. |  |  |  | x
|  | 8.3 | FFCC support |  | x
|  | 8.4 | Settlement affirmation platform |  |  | x
BR9 | Fusion Operate | [5 empty] | x