## Generated
UID | Title | Lead | Support | Description | R metric | P metric
W0 | Cloud value proposition | Product Strategy – Mike S | Andrei | Define value proposition for customers on the Cloud | TBD | TBD
W1 | Modernization | Alex | Leigh, GMs, Ouafa | Deliver the main components of the cloud roadmap: Microservices, Containerization, Multi-tenancy, UX, Operations / DevOps | Product [X] to target state [Y] by time [Z]Example: Product: Essence to Webapp by end of FY22. | # of EPICs delivered in time and budgetExample: By Aug: 20%(20% of what is expected in the 12 months of FY 22 has been done)
W2 | Software delivery and production operations | Leigh | Russ, Bryan, Ouafa, Andrew | FusionOperate: Increase automation through deployment and DevOps across all cloud propositions (FMS, FusionCloud, etc). Support native cloud at scale | % Cloud clients compliant with EA operating standards & policy (measured quarterly) | % automated tests integrated with pipeline
W3 | N-1 compliance (excl. FMS) | Michael M | GMs, Andrew | Institutionalise a release and sales policy to ensure all hosted customers are on the latest GA release | % of Finastra-hosted clients post Feb 1st, 2021 implemented and maintained on N-1 version | % of Finastra client contracts signed with N-1 compliance clause
W4 | FMS / AMS | Andrew | Neil | Develop and implement a 3-year conversion programme to accelerate sales of Fusion Managed Services solutions for LoanIQ, Trade Innovation, GPP and Kondor | FMS accretive SW bookings of [$XM] | FMS SW pipeline of [$XM]
W5 | Cloud sales (excl. FMS) | Hannes | Rudy | Develop and implement GTM and deal support across the sales cycle to accelerate Cloud sales. Scope includes collateral, materials, references, SPP build outs and alignment of product readiness with the messaging / GTM process | Cloud bookings of [$XM] | Cloud pipeline by product by region of [$XM]
W6 | Pricing | Christian | Brad B., Bruce B. | Develop and implement pricing approach for Cloud to ensure pricing takes full account of costs (infrastructure) and workload (e.g., Level 1 support) is moved from client to Finastra when move from on prem to cloud | Pricing approach developed and implemented for all Cloud products | Delivery of milestones per product
W7 | IT role in native Cloud solutions | Russ | Leigh, Bryan | Revamp, rework and modernize network and infrastructure to support cloud at scale. Scope will address network support to deliver and deploy at scale, end to end monitoring and extensive automation | [X%] Cloud clients compliant utilizing modern network connectivity | % network deployment automated% products onboarded to status page
W8 | Customer Support for native Cloud solutions | Michael | Leigh | Implement Cloud customer support model across DevOps, IT and customer support | Number of products with customer self-service capabilities supportability embedded made available to customers | Delivery of milestones per product
W9 | Talent transformation | Clare | Shira, Neeha | Define and deliver skills & capabilities required fordelivering Cloud faster across organization: Product, GCO, CCO. | Actions from plans in place (training, hires, capabilities addressed) | Skills & capabilities plans completed​ (by workstream)

## Eall
Terminology for all to align on
Service Operating Models (SOM)
|  | SaaS | Define FusionCloud (SaaS) SOM via FusionOperate: *full CI/CD automation; *multi*tenant environments; *multi*tenant ops (monitoring, upgrades, …) *no customizations; *n-1
|  | C@S | Define Cloud@Scale SOM via FusionOperate: *full CI/CD automation; *single*tenant customer environments; *multi*tenant ops (monitoring, upgrades, …) *no customizations; *n-1
|  | FMS | Define FMS SOM via FusionOperate: *full CI/CD automation; *single*tenant customer environments; *single*tenant ops (monitoring, upgrades, …) *customizations built via FO's software factory and FFDC APIs *n-3 or better
|  | Partner | Define partner-hosted SOMs by reference to the Finastra-hosted SOMs (FusionCloud, Cloud@Scale, FMS)

## Ew0
UID | Title | Description | R metric | P metric | Lead | Support
W0 | Cloud value proposition | Define value proposition for customers on the Cloud | TBD | TBD | Product Strategy – Mike S | Andrei
UID | Expectation | Description | Acceptance Criteria Artifact | Evidence of correctness
| Analyze segmentation | Break Finastra's space into segments and for each measure the appetite for cloud | Segmentation tree: consolidated tree of segments (verticals, geos, tiers, and breakouts for either) | Data sources (provider, numerical and label data, and date) from which segmentation analysis was derived
Size at each leaf in the segmentation tree
Quantification of how much of that could be cloud
| Analyze "Jobs to be done" / Personas | Using Design Thinking and Clayton Christensens "Jobs to be done" methodology, for each cloud-friendly segment describe the personas and what "struggle" (as in Christensen's approach) they are in. | Narrated diagrams indicating the timeline-based tasks that Personas engage with and where the struggle lies, using standard notations such as BPMN flows or UML sequence diagrams. | Data sources (customer or 3rd party interviews)
| Define Value propositions | Define logical bundle of Finastra capabilities which would address each of the "jobs to be done" for each of the cloud-friendly struggles. May be from a Finastra product or a combination of Finastra products. | Vision Statement for Value Proposition, using the FOR/WHO/THE/THAT/UNLIKE/OUR PRODUCT template from Geoffrey Moore
Logical diagram of capabilities
Mapping to the Finastra products that would provide such capabilities
Mapping to the "Jobs to be done" diagrams with a narration on how the capabilities in question address the "struggle"
| Measure Opportunities's size | For each of the value propositions, establish a revenue projection timeline over the next 3 years assuming that Finastra chooses to get into that space | Revenue projection per proposition expressed as a table (time vs revenue)
| Decide areas to prioritize | Determine the priorities to which investment should be focused | A decision-making model to choose the propositions with the highest ROI
| Fail Fast | Adjust analysis and value propositions as new data comes in, specially around success (or failure) of first market launches | Updated artifacts for segmentation, "jobs to be done"/personas, value props, opportunity sizing, and prioritization

## Ew1
UID | Title | Description | R metric | P metric | Lead | Support
W1 | Modernization | Deliver the main components of the cloud roadmap: Microservices, Containerization, Multi-tenancy, UX, Operations / DevOps | Product [X] to target state [Y] by time [Z]Example: Product: Essence to Webapp by end of FY22. | # of EPICs delivered in time and budgetExample: By Aug: 20%(20% of what is expected in the 12 months of FY 22 has been done) | Alex | Leigh, GMs, Ouafa
UID | Expectation | Description | Acceptance Criteria Artifact | Evidence of correctness
| Finishing line | Description of measurable conditions that, if true, indicate that the modernization journey is over because it met its goals. | List of Value Propositions in scope for product
Numerical business outcome KPIs and targets. Typically: size of CAM expansion, quantification of margin improvements and of any new forms of revenue (for example, perhaps from selling to lower tiers)
Numerical technical KPIs and targets needed to meet business outcome KPIs. Typically: cost-per-tenant, TTM, Quality, QoS, etc.
| Define architecture target | Blueprint for a target state architecture that, if achieved, would deliver the technical KPI targets. | Target-state deployment diagrams
Target-state reliabiliy model
For each KPI, a model to predict what the KPI value would be in the target state architecure
| Define operational target | Model for how product will be operated in the target state | Target-state service operating model
Cost model for target state service operating model
For each KPI of an operational nature, a model to predict what its value would be in the target state operating model.
| Define milestones for journey | Decomposition of modernization journey into "milestones", where each milestone has an identifiable customer-facing value and can be monetized | Enumeration of milestones and when in time they happen
For each milestone, a mapping to a Value Proposition (or portion thereof) that is enabld by the milestone
For each milestone, quantified identification of what business outcome KPIs it enables. Typically: size of CAM expansion, margin improvements, new forms of revenue it enables.
| Commit roadmap | Enumeration of Aha epics over next 4-6 quarters, with a mapping to the milestone(s) they enable | Mapping of Aha epics to the milestones
Mapping of roadmap to modernization tactics
| Commit investment | Projection in time on the amount of investment for the modernization journey | Timeline of how many man-days are committed to modernization for each of the next fiscal years, up to the moment when modernization is done.
| Deliver modernization | Timely on-budget delivery of subsequent milestones until the journey is complete, adhering to EA standards | Burnout of Aha epics corresponding to milestones
Delivery of milestones adhering to the EA standards for each of the modernization tactics

## Ew2
UID | Title | Description | R metric | P metric | Lead | Support
W2 | Software delivery and production operations | FusionOperate: Increase automation through deployment and DevOps across all cloud propositions (FMS, FusionCloud, etc). Support native cloud at scale | % Cloud clients compliant with EA operating standards & policy (measured quarterly) | % automated tests integrated with pipeline | Leigh | Russ, Bryan, Ouafa, Andrew
UID | Expectation | Description | Acceptance Criteria Artifact | Evidence of correctness
| Definition of EA Operating Standards | Define the EA Operating Standards that must be complied with for products going to cloud | CI/CD(GitOps) standards
Reliability standards
Monitoring standards
Testing standards
Security standars
| Define how all cloud propositions can be supported with FusionOperate | Define all operating models and how FusionOperate is used in each of them | Define FusionCloud (SaaS) SOM via FusionOperate: *full CI/CD automation; *multi*tenant environments; *multi*tenant ops (monitoring, upgrades, …) *no customizations; *n-1
Define Cloud@Scale SOM via FusionOperate: *full CI/CD automation; *single*tenant customer environments; *multi*tenant ops (monitoring, upgrades, …) *no customizations; *n-1
Define FMS SOM via FusionOperate: *full CI/CD automation; *single*tenant customer environments; *single*tenant ops (monitoring, upgrades, …) *customizations built via FO's software factory and FFDC APIs *n-3 or better
Define partner-hosted SOMs by reference to the Finastra-hosted SOMs (FusionCloud, Cloud@Scale, FMS)
| Define FusionOperate technical value proposition | Define the scope of FusionOperate capabilities in a way that it addresses all cross-cutting concerns across Finastra products going to cloud, so that they are addressed once, across the whole DevSecOps spectrum (CI/CD, reliability model, security model, etc.) | Architecture blueprint for Software Factory
Architecture blueprint for Operating Platform
Architecture blueprint for Testing Platform
Architecture blueprint for Monitoring Platform
| Deliver FusionOperate | Deliver a Finastra-wide DevSecOps platform based on SDNs, K8s and GitOps | Developer productivity KPIs set and met | Written KPIs and proof of attainment across all FusionOperate platforms (Software Factory, Operating Platform, Testing Platform, Monitoring Platform)
|  |  | Customer onboarding KPIs set and met. KPIs targets must relate to the modernization stream's business outcome KPIs. | Written KPIs and proof of attainment across all FusionOperate platforms (Software Factory, Operating Platform, Testing Platform, Monitoring Platform)
|  |  | Cost-of-operation KPIs set and met. KPIs targets must relate to the modernization stream's business outcome KPIs. | Written KPIs and proof of attainment across all FusionOperate platforms (Software Factory, Operating Platform, Testing Platform, Monitoring Platform)
|  |  | Speed-of-upgrades KPIs set and met. KPIs targets must relate to the modernization stream's business outcome KPIs. | Written KPIs and proof of attainment across all FusionOperate platforms (Software Factory, Operating Platform, Testing Platform, Monitoring Platform)

## Ew3
UID | Title | Description | R metric | P metric | Lead | Support
W3 | N-1 compliance (excl. FMS) | Institutionalise a release and sales policy to ensure all hosted customers are on the latest GA release | % of Finastra-hosted clients post Feb 1st, 2021 implemented and maintained on N-1 version | % of Finastra client contracts signed with N-1 compliance clause | Michael M | GMs, Andrew
UID | Expectation | Description | Acceptance Criteria Artifact | Evidence of correctness
| Update commercial policy | Update commercial policy to ensure that sales contracts empower Finastra to enforce n-1 (except for FMS) | Updated commercial policy for all cloud SOMs except FMS
| Engage in Opportunities desk | Engage in the cloud sales opportunities desks to steer as many opportunities as possible towards the operating models that ensure n-1 (Cloud@Scale, FusionCloud) | Periodic report on opportunities and the SOM they were directed to
| Alert on any n-1 degradation | For cloud sales steered towards SOMs that ensure n-1 (Cloud@Scale, FusionCloud), monitor the customer environments on a permanent basis to ensure that as new product releases occur, the n-1 constraint is enforced (i.e., those environments get upgraded) | Periodic report on customer environments that are on Cloud@Scale or FusionCloud and flagging any n-1 violation

## Ew4
UID | Title | Description | R metric | P metric | Lead | Support
W4 | FMS / AMS | Develop and implement a 3-year conversion programme to accelerate sales of Fusion Managed Services solutions for LoanIQ, Trade Innovation, GPP and Kondor | FMS accretive SW bookings of [$XM] | FMS SW pipeline of [$XM] | Andrew | Neil
UID | Expectation | Description | Acceptance Criteria Artifact | Evidence of correctness
Adopt FFDC as exclusive SDK for all customizations
| Adopt of Fusion Operate as only delivery mechanism |  | Customizations built with FO's Software Factory
Full CI/CD automation, with GitOps
Adoption of FO's Monitoring Platform - logs and traces done consistently
Networking via FO's FusionDelivery (SDN)
G/S developers to provide AppOps for the customizations they write
Manage margins and cost structure
| Align sales pipeline with Value Propositions | Focus on preparing GTMs for the value propositions identified and prioritized in workstream W0

## Ew5
UID | Title | Description | R metric | P metric | Lead | Support
W5 | Cloud sales (excl. FMS) | Develop and implement GTM and deal support across the sales cycle to accelerate Cloud sales. Scope includes collateral, materials, references, SPP build outs and alignment of product readiness with the messaging / GTM process | Cloud bookings of [$XM] | Cloud pipeline by product by region of [$XM] | Hannes | Rudy
UID | Expectation | Description | Acceptance Criteria Artifact | Evidence of correctness
| Align sales pipeline with Value Propositions | Focus on preparing GTMs for the value propositions identified and prioritized in workstream W0

## Ew6
UID | Title | Description | R metric | P metric | Lead | Support
W6 | Pricing | Develop and implement pricing approach for Cloud to ensure pricing takes full account of costs (infrastructure) and workload (e.g., Level 1 support) is moved from client to Finastra when move from on prem to cloud | Pricing approach developed and implemented for all Cloud products | Delivery of milestones per product | Christian | Brad B., Bruce B.
UID | Expectation | Description | Acceptance Criteria Artifact | Evidence of correctness
| Align packaging with Value Propositions | Define packaging associated to the prioritized value propositions from workstream W0 | Possible bundling models for each value prop, along dimensions like: * What is licensed separately * What is sold via partners, under a variety of scenarios (white label, OEM, etc.)
For each bundling model, analyze monetization potential by identifying what fees can be commanded given the segmentation sizing analysis from stream W0 * Upfront fees * Usage fees * Support fees * Renewal fees * Partner fees etc.
| Define pricing | From analysis of bundling models and monetization models, determine the package(s) and associated fees that will be taken to market | Definition of packages (as bundles) and the pricing structure for each.
| Ensure profitability | Identify the full cost for the packaging in question, and ensure that price is set so that a target margin can result

## Ew7
UID | Title | Description | R metric | P metric | Lead | Support
W7 | IT role in native Cloud solutions | Revamp, rework and modernize network and infrastructure to support cloud at scale. Scope will address network support to deliver and deploy at scale, end to end monitoring and extensive automation | [X%] Cloud clients compliant utilizing modern network connectivity | % network deployment automated% products onboarded to status page | Russ | Leigh, Bryan
UID | Expectation | Description | Acceptance Criteria Artifact | Evidence of correctness
| Align with Fusion Operate | Understand the FusionOperate strategy around cloud-native networking, service mesh, Fusion Delivery and GitOps, to focus on areas where IT's support is needed, and avoid duplication by not involving IT into areas that FO plans to take care of.

## Ew8
UID | Title | Description | R metric | P metric | Lead | Support
W8 | Customer Support for native Cloud solutions | Implement Cloud customer support model across DevOps, IT and customer support | Number of products with customer self-service capabilities supportability embedded made available to customers | Delivery of milestones per product | Michael | Leigh
UID | Expectation | Description | Acceptance Criteria Artifact | Evidence of correctness
| Align with Fusion Operate | Define how customer support would work for each of the service operating models that rely on Fusion Operate (FusionCloud, Cloud@Scale, FMS, and partner-hosted)

## Ew9
UID | Title | Description | R metric | P metric | Lead | Support
W9 | Talent transformation | Define and deliver skills & capabilities required fordelivering Cloud faster across organization: Product, GCO, CCO. | Actions from plans in place (training, hires, capabilities addressed) | Skills & capabilities plans completed​ (by workstream) | Clare | Shira, Neeha
UID | Expectation | Description | Acceptance Criteria Artifact | Evidence of correctness
| Launch FusionOperate - oriented training | Devise and launch training programs in the technologies that development teams need in order to leverage the self-service capabilities in FusionOperate and take ownership of their production deliveries | Launch OpenShift training
Launch K8S/SDN-based Networking training
Launch GitOps training
Launch AppOps training
Launch Terraform training