## Posting Label
Posting Label
manifestAPI | delivery-planning.journeys.a6i.io/v1a
organization | My Corp
knowledgeBase | Production
recordedBy | jill.thearchitect@mycorp.com
estimatedBy | joe.thedevhead@mycorp.com
estimatedOn | 2021-04-29
priorVersion.0 | 1
product | FusionOpus
journey | Modernization
scenario | Default
scoringCycle | Dec 2020
scoringMaturity | Draft
planType | Marathon
variant | burnout
priorVersion.2 | 1
priorVersion.3 | 1
data.kind.0 | big-rock
data.range.0 | B2:E10
data.sheet.0 | Assertions
data.kind.2 | big-rock-estimate
data.range.2 | F2:F10
data.sheet.2 | Assertions
data.kind.3 | investment
data.range.3 | H2:I10
data.sheet.3 | Assertions

## Assertions
big-rock.0 |  |  |  | big-rock-estimate.1 | investment.2
UID | big-rock | medium rock | small rock | effort | period | Incremental | Cumulative
BR1 | B2C APIs | Integration APIs |  | 2000 | FY 2021 | 3584 | 3584
|  | Digital APIs |  | 2050 | FY 2022 | 5207 | 8791
BR2 | Cloudification – Remove Oracle Dependency | Prepare schema |  | 6600 | FY 2023 | 5575 | 14366
|  |  | Remove stored procedures | 600 | FY 2024 | 5800 | 20166
|  | Remove XA |  | 3000 | FY 2025 | 5860 | 26026
BR3 | Modernization – Persona Based Dashboard, Improved UI/UX -*CHANGED |  |  | 4500 | FY 2026 | 3600 | 29626
BR4
BR5 | Containerization |  |  | 525
| Total: |  |  | 19275