## Posting Label
Posting Label
manifestAPI | delivery-planning.journeys.a6i.io/v1a
organization | my-corp
knowledgeBase | production
recordedBy | frustrated.projectmanager@his-corp.com
estimatedBy | always.late@my-corp.com
estimatedOn | 2021-08-23
priorVersion.0 | 2
product | FusionOpus
journey | modernization
scenario | Default
scoringCycle | Dec 2020
scoringMaturity
priorVersion.1 | 1
data.kind.0 | big-rock
data.range.0 | B8:G17
data.sheet.0 | Assertions
readOnly.0 | TRUE
data.kind.1 | modernization-milestone
data.range.1 | H2:N26
data.sheet.1 | Assertions

## Assertions
modernization-milestone.1
[6 empty] | UID | M1 |  | M2 | M3 | M4
[6 empty] | milestone | SME market | POC for SMEs | SME market.1 | New UX | Cloud EA | Cloud GA
[6 empty] | Date | Q3 FY20 | Q1 FY 20 | Q3 FY21 | Q4 FY21 | Q4 FY22 | Q2 FY 23
[6 empty] | Comment |  | Added because we are late with M2 |  |  | Scope reduced; rest will be done later | Delayed (used to complete in M4)
[6 empty] | Theme | CAM expansion | Early adopters | Margin improvement | New UX | Cloud hybrid | Cloud native
big-rock.0
UID | big-rock | UID-1 | medium rock | UID-2 | small rock
BR1 | B2C APIs |  |  |  |  | BR1
|  | BR1.1 | Integration APIs |  |  | BR1.MR1 | x
|  | BR1.2 | Digital APIs |  |  | BR1.MR2 |  | x
BR2 | Cloudification – Remove Oracle Dependency |  |  |  |  | BR2
|  | BR2.1 | Prepare schema |  |  | BR2.MR1 |  |  |  | x
|  |  |  | BR2.1.1 | Remove stored procedures | BR2.MR1.SR1 | [5 empty] | x
|  | BR2.2 | Remove XA |  |  | BR2.MR2 |  |  |  |  | x
BR3 | Modernization – Persona Based Dashboard, Improved UI/UX -*CHANGED |  |  |  |  | BR3 |  |  | x
BR5 | Containerization |  |  |  |  | BR5 |  |  | x